## All projects
ProjectID | Activities | Owner | App.Engg | Start Date | End Date | Activity status | Weightage | Progress Status | %Complete | Dependency | Dependency owner | Dependency status | Dependency complition date | W%complition
PRO1 | DMM-KEYSIGHT34465A | Sneha | Sachith | 2024-09-20 | 2024-11-10 | Closed | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2024-08-11 | 5%
PRO1 | LED Analyser-Feasa -Feasa 5F | Manik | Sachith | 2024-10-16 | 2024-10-18 | OPEN | 10% | Not Started | 1% |  |  |  |  | 0.1%
PRO1 | Radio Test Head - R&S-CMW100 | Sneha | Sachith | 2024-09-20 | 2024-11-10 | Closed | 10% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2024-08-11 | 10%
PRO1 | Reference Instrument for Pressure Sensor-Mensor-CPT6180 | Sneha | Sachith | 2024-09-16 | 2024-11-10 | Closed | 5% | Completed | 100% | Information Required | Prasad | CLOSED | 2024-08-11 | 5%
PRO1 | LoRa Gateway Module – US915-RAK Wireless-RAK7268V2 | Sneha | Sachith | 2024-10-22 | 2024-10-24 | Closed | 5% | Completed | 100% | Information Required | Prasad | CLOSED | 2024-08-11 | 5%
PRO1 | LoRa Gateway Module – EU858-RAK Wireless-RAK7268V2 | Sneha | Sachith | 2024-10-25 | 2024-10-27 | Closed | 5% | Completed | 100% | Information Required | Prasad | CLOSED | 2024-08-11 | 5%
PRO1 | Reference Instrument for Sensors Simulation-D.02-002-Nano DST | Sneha | Sachith | 2024-09-27 | 16/10/2024 | Closed | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2024-08-11 | 5%
PRO1 | Bluetooth Module-Nordic-NRF52840 | Sneha | Sachith | 2024-10-16 | 2024-10-30 | Closed | 5% | Completed | 100% | Script Required | Customer | CLOSED | 2024-08-11 | 5%
PRO1 | Testing01 | sachith | Sachith | 2024-10-11 | 2024-10-17 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO1 | Internal Sign Off01 | sachith | Sachith | 2024-10-11 | 2024-10-17 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO1 | Customer Sign off01 | Prasad | Sachith | 2024-11-18 | 2024-11-23 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO1 | Fixed Scanner -Keyence -SR-X100N | Anusha | Sachith | 2024-10-18 | 2024-10-23 | On Hold | 5% | In Progress | 50% | Device Model ,commands | Murali | CLOSED | 2024-11-11 | 2.5%
PRO1 | Digital I/O Interface-ICPIO | Anusha | Sachith | 2024-09-18 | 2024-09-23 | CLOSED | 15% | Completed | 100% |  |  |  |  | 15%
PRO1 | UART Communication | Anusha | Sachith | 2024-10-24 | 2024-10-26 | CLOSED | 15% | Completed | 100% | Proper connectivity needed | Customer | CLOSED | 30/09/2024 | 15%
PRO10 | SMU ( Source Measuring Unit )-GW-GSM-20H10 | Sneha | Adithya | 2024-11-12 | 2024-11-16 | CLOSED | 40% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-12-02 | 40%
PRO10 | Grading Machine For MOSFET(Turntide) | Pradeep | Adithya | 2024-11-22 | 2025-01-24 | CLOSED | 40% | Completed | 100% |  |  |  |  | 40%
PRO10 | testing10 | Mutturaman | Adithya | 2024-11-12 | 2025-01-24 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO10 | Customer signoff10 | Prasad | Adithya | 2024-11-12 | 2025-01-24 | OPEN | 5% | In Progress | 90% |  |  |  |  | 4.5%
PRO11 | MTS Main screen | Manik | Manik | 2024-10-03 | 2024-12-31 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO12 | Object detection-Template matching algo development | Sunita | Sathya | 2024-10-21 | 2024-10-26 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO12 | object detection-Tm testing and feature extraction algo development | Sunita | Sathya | 2024-10-28 | 2024-11-02 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | object detection-feature extraction development and testing | Sunita | Sathya | 2024-11-04 | 2024-11-09 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | Object detection-research on new algorithm | Sunita | Sathya | 2024-11-11 | 2024-11-16 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | Color identification-Get set pixel algo development | Sunita | Sathya | 2024-11-12 | 2024-11-16 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | Color identification-testing and inrange algo development | Sunita | Sathya | 2024-11-18 | 2024-11-23 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | Color identification-research on new algorithm | Sunita | Sathya | 2024-11-25 | 2024-11-30 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | Blob detection-contour algo development | Sunita | Sathya | 2024-11-26 | 2024-11-30 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | Blob detection-contour algo development testing | Sunita | Sathya | 2024-12-02 | 2024-12-07 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | Blob detection-research on new algorithm | Sunita | Sathya | 2024-12-09 | 2024-12-14 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | Intensity identification-get set pixel algo development | Sunita | Sathya | 2024-12-10 | 2024-12-14 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | Intensity identification--research on new algorithm | Sunita | Sathya | 2024-12-16 | 2024-12-21 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | OCR reading-paddle ocr development | Sunita | Sathya | 2024-12-23 | 2024-12-28 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | OCR reading-tesseract ocr development | Sunita | Sathya | 2024-12-30 | 2025-01-04 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO12 | OCR reading-research on new algorithm | Sunita | Sathya | 2025-01-06 | 2025-01-11 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO12 | UI Development(main window,training and testing window) | Pradeep | Sathya | 2024-10-17 | 2024-10-26 | On Hold | 2% | In Progress | 100% |  |  |  |  | 2%
PRO12 | Training window responsive and database | Pradeep | Sathya | 2024-10-28 | 2024-11-02 | On Hold | 3% | In Progress | 100% |  |  |  |  | 3%
PRO12 | Object detection-Template matching algo development adding to training area | Pradeep | Sathya | 2024-11-04 | 2024-11-09 | On Hold | 5% | In Progress | 100% |  |  |  |  | 5%
PRO12 | object detection-Tm testing and feature extraction algo development adding to training area | Pradeep | Sathya | 2024-11-11 | 2024-11-16 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO12 | object detection-feature extraction development and testing adding to training area | Pradeep | Sathya | 2024-11-18 | 2024-11-23 | On Hold | 5% | In Progress | 100% |  |  |  |  | 5%
PRO12 | Color identification-Get set pixel algo development adding to training area | Pradeep | Sathya | 2024-11-25 | 2024-11-30 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO12 | Color identification-testing and inrange algo development adding to training area | Pradeep | Sathya | 2024-12-02 | 2024-12-07 | On Hold | 5% | In Progress | 100% |  |  |  |  | 5%
PRO12 | Blob detection-contour algo development adding to training area | Pradeep | Sathya | 2024-12-09 | 2024-12-14 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO12 | Blob detection-contour algo development testing adding to training area | Pradeep | Sathya | 2024-12-16 | 2024-12-21 | On Hold | 5% | In Progress | 100% |  |  |  |  | 5%
PRO12 | Intensity identification-get set pixel algo development adding to training area | Pradeep | Sathya | 2024-12-23 | 2024-12-28 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO12 | OCR reading-paddle ocr development adding to training area | Pradeep | Sathya | 2024-12-30 | 2025-01-04 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO12 | OCR reading-tesseract ocr development adding to training area | Pradeep | Sathya | 2025-01-06 | 2025-01-11 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO13 | Barcode Scanner - Fixed --Symbol/Zebra | Anusha | Muthuraman | 2024-11-12 | 2024-11-16 | CLOSED | 5% | Completed | 100% |  |  | CLOSED | 2025-01-01 | 5%
PRO13 | Scara Robot with Controller MAKE-Epson , PART NO-T3 | Sneha | Muthuraman | 2024-11-12 | 2024-11-16 | CLOSED | 10% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-01 | 10%
PRO13 | PPS - GW-Instek -GPP-2323 | Sneha | Muthuraman | 2024-11-12 | 2024-11-16 | CLOSED | 3% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-01 | 3%
PRO13 | DMM MAKE-GW-Instek, PART NO-GDM-8261A | Sneha | Muthuraman | 2024-11-12 | 2024-11-16 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-01 | 5%
PRO13 | DC Electronic Load MAKE- BKP, PART NO-8061 | Sneha | Muthuraman | 2024-11-12 | 2024-11-16 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-01 | 5%
PRO13 | CAN Transciever MAKE- NI ,PART NO-USB-8502 | Anil | Muthuraman | 2024-11-15 | 2024-11-30 | CLOSED | 50% | Completed | 100% | Customer Part | Chandan | CLOSED | 17-12-2024 | 50%
PRO13 | testing13 | Sathya | Muthuraman | 2024-11-15 | 2024-11-30 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO13 | customer signoff13 | Prasad | Muthuraman | 2024-11-15 | 2024-11-30 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO14 | CANalyzer PRO Software for Flashing | Sneha | Sachith | 2024-12-09 | 2024-12-11 | CLOSED | 35% | Completed | 100% | Flashing through Software | Prasad | CLOSED | 2024-09-12 | 35%
PRO14 | Testing14 | Sushmitha | Sachith | 2024-11-12 | 2025-02-08 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO14 | customer signoff 14 | Prasad | Sachith | 2024-11-12 | 2024-11-30 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO15 | Keypad inspection | Pradeep | Sachith | 2024-11-18 | 2024-11-27 | Closed | 80% | Completed | 100% | Master Variant Needed for one Variant | Customer | CLOSED |  | 80%
PRO15 | Testing15 | Sachith | Sachith | 2024-11-25 | 2024-11-29 | Closed | 10% | Completed | 100% |  |  |  |  | 10%
PRO15 | coustomer signoff15 | Prasad | Sachith | 2024-11-25 | 2024-11-29 | Closed | 10% | Completed | 100% |  |  |  |  | 10%
PRO16 | Multiple line traceability | Manik | Sathya | 2024-12-02 | 2025-01-25 | CLOSED | 70% | Completed | 100% |  | Customer | CLOSED |  | 70%
PRO16 | testing16 | Sushmitha | Sathya | 2024-12-02 | 2025-01-25 | CLOSED | 15% | Completed | 100% |  |  |  |  | 15%
PRO16 | customer signoff16 | Prasad | Sathya | 2024-12-02 | 2025-01-25 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO2 | Testing02 | Mutturaman | Mutturaman | 2024-09-20 | 2024-09-25 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO2 | Internal Sign Off02 | Mutturaman | Mutturaman | 2024-09-25 | 2024-09-30 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO2 | Label Printer- CAB SQUIX 4/600M | Anusha | Mutturaman | 2024-09-26 | 2024-09-29 | CLOSED | 10% | Completed | 100% | Ribbon/Label | Prasad | CLOSED | 2024-11-20 | 10%
PRO2 | Hand Held Scanner -Datalogic or equivalent | Anusha | Mutturaman | 2024-09-27 | 2024-09-28 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO14 | Read DBC File Through CAN | Sushmitha | Sachith | 2024-12-12 | 2024-12-17 | CLOSED | 35% | Completed | 100% | Require Support | Customer | CLOSED | 2025-01-01 | 35%
PRO2 | Calculations | Sneha | Mutturaman | 2024-09-20 | 2024-09-29 | CLOSED | 10% | Completed | 100% | Formula | Murali | CLOSED | 22/9/2024 | 10%
PRO2 | LCRMeter -GWINSTEKLCR6100 | Sneha | Mutturaman | 2024-09-11 | 2024-09-29 | CLOSED | 10% | Completed | 100% | Instrument | Murali | CLOSED | 22/9/2024 | 10%
PRO2 | Customer Sign off02 | Prasad | Mutturaman | 2024-09-30 | 2024-10-05 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO2 | ICPDIO | Anusha | Mutturaman | 2024-09-26 | 2024-09-27 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO2 | Naxnova Reports | Anusha | Mutturaman | 2024-10-24 | 2024-11-23 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO2 | GUI Screen Modification | Manik | Mutturaman | 2024-10-18 | 2024-10-22 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO3 | Testing03 | Mutturaman | Sathya | 2024-10-22 | 2024-10-17 | OPEN | 20% | Not Started | 1% |  |  |  |  | 0.2%
PRO3 | Internal Sign Off03 | Mutturaman | Sathya | 2024-10-17 | 2024-10-22 | OPEN | 10% | Not Started | 1% |  |  |  |  | 0.1%
PRO3 | AC Programmable Power Source, 230VAC,1A -GW /Equivalent | Sneha | Sathya | 2024-09-20 | 2024-11-01 | On Hold | 20% | Completed | 100% | The model has not been decided. | Customer | OPEN |  | 20%
PRO3 | Digital Multimeter - GW /Equivalent | Sneha | Sathya | 2024-09-20 | 2024-11-01 | On Hold | 10% | Completed | 100% | The model has not been decided. | Customer | OPEN |  | 10%
PRO3 | Customer Sign off03 | Prasad | Sathya | 2024-11-01 | 2024-11-06 | OPEN | 10% | Not Started | 1% |  |  |  |  | 0.1%
PRO3 | Digital I/O Interface - Distributed I/O ICPDAS | Anusha | Sathya | 2024-09-12 | 2024-09-17 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO4 | Scanner - Cognex - DMR152S | Anusha | Mutturaman | 2024-10-27 | 2024-10-28 | On Hold | 10% | Unit test | 90% | Device | Murali | OPEN |  | 9%
PRO4 | CAN- National Instruments - 8502(UDS) | Sneha | Mutturaman | 2024-09-20 | 2024-10-10 | On Hold | 10% | Unit test | 80% | Customer Part | Customer | OPEN |  | 8%
PRO4 | Testing04 | Sachith | Mutturaman | 2024-09-13 | 2024-10-10 | On Hold | 10% | Not Started | 1% |  |  |  |  | 0.1%
PRO4 | HIPOTTester- MicroTest7631 | Sneha | Mutturaman | 2024-09-20 | 2024-10-10 | On Hold | 10% | Unit test | 80% | Machine is not ready | Chandan | OPEN |  | 8%
PRO4 | NI DIO ToolMonitor | Anusha | Mutturaman | 2024-09-25 | 2024-10-09 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO4 | I-TAC | Sneha | Mutturaman | 2024-09-13 | 2024-10-10 | On Hold | 10% | Not Started | 1% | Information Required | Customer | OPEN |  | 0.1%
PRO4 | Power meter Yokogawa-Wt310 | Sneha | Mutturaman | 2024-09-20 | 2024-10-10 | On Hold | 10% | Unit test | 80% | Machine is not ready | Murali | OPEN |  | 8%
PRO4 | PPS -ITECHIT6005C | Sneha | Mutturaman | 2024-09-20 | 2024-10-10 | On Hold | 10% | Unit test | 80% | Machine is not ready | Murali | OPEN |  | 8%
PRO4 | Internal Sign Off04 | Sachith | Mutturaman | 2024-09-13 | 2024-10-15 | On Hold | 10% | Not Started | 1% |  |  |  |  | 0.1%
PRO4 | Customer Sign off04 | Prasad | Mutturaman | 2024-09-13 | 2024-10-30 | On Hold | 10% | Not Started | 1% |  |  |  |  | 0.1%
PRO4 | NI DIO Driver | Anusha | Mutturaman | 2024-11-09 | 2024-11-15 | On Hold | 5% | In Progress | 90% |  |  |  |  | 4.5%
PRO5 | Digital I/O(ICP CON) | Anusha | Sathya | 2024-09-01 | 2024-09-03 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | Testing05 | Sathya | Sathya | 2024-09-26 | 2024-10-10 | OPEN | 10% | In Progress | 90% |  |  |  |  | 9%
PRO5 | Internal Sign Off05 | Sathya | Sathya | 2024-09-26 | 2024-10-10 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO5 | CAN(PCAN)&NI-XNET | Sneha | Sathya | 2024-09-20 | 2024-10-08 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | DMM - GWInstekGDM8261 | Anusha | Sathya | 2024-09-20 | 2024-10-08 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | frequency generator-Unitronics(V130-J-T2)(MODBUS-RTU) | Sneha | Sathya | 2024-09-12 | 2024-09-28 | CLOSED | 4% | Completed | 100% |  |  |  |  | 4%
PRO5 | Vision Communication (TCP IP) | Sneha | Sathya | 2024-09-12 | 2024-09-28 | CLOSED | 4% | Completed | 100% |  |  |  |  | 4%
PRO5 | Oscilloscope- TBS10S2C | Sneha | Sathya | 2024-09-18 | 2024-09-26 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | PPS- GWInstek2323 | Sneha | Sathya | 2024-09-20 | 2024-09-26 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO5 | Printer(Zebra) | Anusha | Sathya | 2024-10-04 | 2024-10-05 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | Vision(OCR) | Sunita | Sathya | 2024-09-23 | 2024-10-07 | CLOSED | 100% | Completed | 90% |  |  |  |  | 90%
PRO5 | Vision(OCR, Traning window) | Pradeep | Sathya | 2024-09-23 | 2024-10-10 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO5 | Calculation | Sneha | Sathya | 2025-01-01 | 2025-01-01 | CLOSED |  | Completed | 100% |  |  |  |  | 0%
PRO5 | Scanner(Datalogic) | Anusha | Sathya | 2024-10-08 | 2024-10-10 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | Customer Sign off05 | Prasad | Sathya | 2024-10-10 | 2024-10-20 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO5 | GUI Screen Modification(Dual fixtures) | Manik | Sathya | 2024-10-15 | 2024-11-06 | OPEN | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | Vision Algorithms (OCR ,Template Matching,Multiple Template Matching, Feature Extraction,Color Picker, Intensity value Extraction,Blob Algorithm Development and Training ) | Pradeep | Sathya | 2024-10-11 | 2024-11-04 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | Report | Anusha | Sathya | 2024-11-06 | 2024-11-11 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO5 | MTS Screen Modification(Dual fixtures) | Manik | Sathya | 2024-11-08 | 2024-11-12 | OPEN | 5% | Completed | 100% |  |  |  |  | 5%
PRO6 | 6TL- Matrix (YAV90069) | Anusha | Sachith | 2024-09-20 | 2024-09-25 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO6 | Testing06 | Sachith | Sachith | 2024-09-25 | 2024-10-05 | OPEN | 5% | In Progress | 30% |  |  |  |  | 1.5%
PRO6 | Internal Sign Off06 | Sachith | Sachith | 2024-10-05 | 2024-10-20 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO6 | Customer Sign off06 | Prasad | Sachith | 2024-10-30 | 2024-10-30 | OPEN | 5% | Not Started | 1% |  |  |  |  | 0.05%
PRO6 | PPS - ITM7723 (ITECH AC Power Supply 300V, 12A ) | Sneha | Sachith | 2024-09-21 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | OPEN |  | 5%
PRO6 | PPS - GWInstekPFR100M (DC Power Supply 250V, 2A) | Sneha | Sachith | 2024-09-20 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | OPEN |  | 5%
PRO6 | PPS- GWInstekPPX10H01(DC Power Supply 100V, 1A ) | Sneha | Sachith | 2024-09-21 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | OPEN |  | 5%
PRO6 | PPS- GWInstekAPS7050 (AC Power Supply 310V, 2.1A) | Sneha | Sachith | 2024-09-20 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | OPEN |  | 5%
PRO6 | DMM- GWInstek-GDM9061(Digital Multimeter 6 ½ Digit) | Sneha | Sachith | 2024-09-21 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | OPEN |  | 5%
PRO6 | NI-CAN (784661-01) | Sneha | Sachith | 2024-09-20 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | OPEN |  | 5%
PRO6 | Flashing For DTU | Sneha | Sachith | 2024-12-05 | 2024-12-07 | CLOSED | 15% | Completed | 100% | Bench Setup | Basavraju | Closed | 2024-12-05 | 15%
PRO6 | Flashing For OBC | Sneha | Sachith | 2024-12-13 | 2024-12-14 | OPEN | 5% | In Progress | 100% | Flashing Manualy | Sachith | CLOSED |  | 5%
PRO6 | Modbus Communication For Multi Function Meter | Sneha | Sachith | 2024-12-04 | 2024-12-05 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO6 | PPS - IT6018C300225 (ITECH DC Power Supply 300V, 225A Bidirectional) | Sneha | Sachith | 2024-09-20 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED |  | 5%
PRO6 | PEAK- USBCAN | Sneha | Sachith | 2024-09-21 | 2024-10-15 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED |  | 5%
PRO6 | OBC - Rs232 Communication | Anusha | Sachith | 2024-10-30 | 2024-11-26 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO7 | Testing07 | Sathya | Mutturaman | 2024-09-26 | 2024-10-10 | OPEN | 10% | Not Started | 90% |  |  |  |  | 9%
PRO7 | Internal Sign Off07 | Sathya | Mutturaman | 2024-09-26 | 2024-10-10 | OPEN | 10% | Not Started | 90% |  |  |  |  | 9%
PRO7 | Traceability(syrma) | Manik | Mutturaman | 2024-09-20 | 2024-09-28 | ClOSED | 25% | Completed | 100% |  |  |  |  | 25%
PRO7 | Customer Sign off07 | Prasad | Mutturaman | 2024-09-28 | 2024-10-19 | OPEN | 5% | Not Started | 40% |  |  |  |  | 2%
PRO7 | Traceability testing(syrma) | Manik | Sushmitha | 2024-09-25 | 2024-09-30 | ClOSED | 15% | Completed | 100% |  |  |  |  | 15%
PRO7 | PLC Programming(syrma) | Prabu | Mutturaman | 2024-11-05 | 2024-11-29 | ClOSED | 5% | Completed | 100% | Application discussion, Final IO list, Sequence | Vithal,Rajesh,Muthu Raman/Sathyamoorthy | CLOSED | 2024-11-29 | 5%
PRO7 | Modbus Programming for Gantry Robot | Sneha | Mutturaman | 2024-11-04 | 2024-11-11 | ClOSED | 15% | Completed | 100% |  |  |  |  | 15%
PRO7 | Report | Manik | Sushmitha | 2024-11-11 | 2024-11-13 | ClOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | UID generator, label printing(TSC TE210) | Anusha | Sushmitha | 2024-10-03 | 2024-10-06 | CLOSED | 8% | Completed | 100% |  |  |  |  | 8%
PRO8 | Replace "rework" with "rework done" while approving rework. | Manik | Sushmitha | 2024-10-18 | 2024-10-21 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO8 | Manual pass needs to be removed. | Manik | Sushmitha | 2024-10-18 | 2024-10-21 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO8 | Customer Sign off08 | Prasad | Sushmitha | 2024-07-01 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Testing 08 | Sushmitha | Sushmitha | 2024-07-01 | 2024-10-31 | CLOSED | 20% | Completed | 100% |  |  |  |  | 20%
PRO8 | UID generator should be based on operator login. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Implement station-wise operator login. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Rework station should be identified by station name. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO8 | Equipment ID needs to be changed. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% | Yazaki need to provide the names | Customer | CLOSED | 2024-12-23 | 5%
PRO8 | Message box should display for at least 5 seconds, and the error message needs to be altered. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 1% | Completed | 100% |  |  |  |  | 1%
PRO8 | FIFO option should be provided. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Enable/disable option for FIFO should be available. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Plan for what happens when the UID generator's serial number reaches 999999. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Standard name should be displayed on the dashboard. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Report needs to be updated (single report). | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% | Report format should be given | Customer | CLOSED | 2024-12-23 | 5%
PRO8 | Measurement data needs to be confirmed by the customer. | Manik | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% | Information needed | Customer | CLOSED | 2025-01-31 | 5%
PRO8 | User manual | Sushmitha | Sushmitha | 2024-10-18 | 2024-10-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | PLC Programing (yazaki) | Prabu | Prabu | 2024-10-01 | 2024-11-15 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO8 | Barcode Generate plugin | Anusha | Mutturaman | 2024-11-23 | 2024-11-18 | CLOSED | 3% | Completed | 100% |  |  |  |  | 3%
PRO9 | PPS APM SP300VAC5000W | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-02 | 5%
PRO9 | PPS DC Bidirectional ITECH IT6005C – 80-150 | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-02 | 5%
PRO9 | PPS DC Bidirectional ITECH IT6006C-300-75 | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-02 | 5%
PRO9 | Controller Hantas mdc-26 | Sneha | Mutturaman/Sathya | 2024-12-23 | 2024-12-27 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO9 | Modbus Communication For Gantry Robot | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO9 | IR Tester Microtest 7631 | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% | Machine is not ready |  |  |  | 5%
PRO9 | DMM Keysight 34456A | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% | Machine is not ready | Murali | CLOSED | 2025-01-02 | 5%
PRO9 | CAN UDS NI 8502-01 | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | OPEN | 5% | In Progress | 70% | DLL required | Customer | OPEN |  | 3.5%
PRO9 | Efficiency | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO9 | CAN Transceiever NI 8502-01 | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 5% | Completed | 100% | Require Support | Prasad |  |  | 5%
PRO9 | Measurment Data | Sneha | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | OPEN | 10% | In Progress | 90% | Information Required | Murali | CLOSED | 2025-01-02 | 9%
PRO9 | Traceability | Manik | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | CLOSED | 20% | In Progress | 80% |  |  |  |  | 16%
PRO9 | Testing09 | Mutturaman | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | OPEN | 5% | Not Started | 50% |  |  |  |  | 2.5%
PRO9 | customer signoff09 | Prasad | Mutturaman/Sathya | 2024-12-24 | 2024-12-27 | OPEN | 2% | Not Started | 1% |  |  |  |  | 0.02%
PRO2 | Packing station | Manik | Mutturaman | 2024-11-30 | 2024-12-05 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO12 | River Rider | Sunita | Sachith | 2024-12-04 | 2024-12-31 | On Hold | 5% | In Progress | 100% |  |  |  |  | 5%
PRO7 | Uid Generator | Manik | Mutturaman | 2024-12-04 | 2024-12-05 | ClOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO6 | DTU - Rs232 Communication | Anusha | Sachith | 2024-10-30 | 2024-11-26 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO14 | MCU - Report | Anusha | Sachith | 2024-12-17 | 2024-12-20 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO8 | DB Integration | Manik | Sushmitha | 2024-12-19 | 2025-01-08 | CLOSED | 2% | Completed | 100% | Information needed | Customer | CLOSED | 2025-02-06 | 2%
PRO17 | PPS | Sushmitha | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 10% | Completed | 80% |  |  |  |  | 8%
PRO17 | DMM | Sushmitha | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 15% | Completed | 80% |  |  |  |  | 12%
PRO17 | CAN Communication | Sushmitha | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 15% | Completed | 1% | Can details required | Chandan | CLOSED |  | 0.15%
PRO17 | Flasher | Sushmitha | Basavraj | 2025-03-04 | 2025-03-10 | CLOSED | 10% | Completed | 50% | BEV Varient not working, | Chandan | CLOSED |  | 5%
PRO17 | UART | Sushmitha | Basavraj | 2025-03-04 | 30/10/2025 | CLOSED | 5% | Completed | 1% |  |  |  |  | 0.05%
PRO17 | Oscilloscope | Sushmitha | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 15% | Completed | 1% | Oscilloscope Bench Setup | Chandan | CLOSED |  | 0.15%
PRO17 | MTS ui (FTM) | Pradeep | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 15% | Completed | 100% |  |  |  |  | 15%
PRO17 | Testing17 | Sachith | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 5% | Completed | 1% |  |  |  |  | 0.05%
PRO17 | customer signoff17 | Prasad | Basavraj | 2024-12-26 | 2025-02-10 | CLOSED | 5% | Completed | 1% |  |  |  |  | 0.05%
PRO7 | Image display | Anil | Mutturaman | 2025-01-23 | 2025-01-31 | OPEN | 5% | Not Started | 100% |  |  |  |  | 5%
PRO9 | Image display(minda) | Anil | Mutturaman/Sathya | 2025-01-23 | 2025-01-31 | Open | 3% | Not Started | 100% |  |  |  |  | 3%
PRO10 | Grading Machine for MOSFET - Report | Anusha | Sachith | 2025-01-27 | 2025-01-28 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO13 | EOL For Wireless Chargeing Module(WCM) - Barcode Generation | Anusha | Muthuraman | 2025-01-01 | 2025-01-23 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO13 | EOL For Wireless Chargeing Module(WCM) - Master Data | Anusha | Muthuraman | 2025-01-01 | 2025-01-23 | CLOSED | 2% | Completed | 100% |  |  |  |  | 2%
PRO9 | Assembly line for OBC 3.3KW - Master Data and Prn for Barcode Generation | Anusha | Sathya | 2025-01-24 | 2025-01-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO9 | Assembly line for OBC 3.3KW - Barcode Generation | Manik | Sathya | 2025-01-24 | 2025-01-31 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO18 | Traceability(Turntide) | Manik | Adithya | 2025-02-07 | 2025-03-07 | OPEN | 60% | In Progress | 100% | Information needed ,Master data required | Daniel | CLOSED |  | 60%
PRO18 | DB Integration(Turntide) | Manik | Adithya | 2025-02-08 | 2025-03-08 | OPEN | 10% | In Progress | 90% | Information needed | Daniel | OPEN |  | 9%
PRO18 | Image display(Turntide) | Anil | Adithya | 2025-02-07 | 2025-03-07 | OPEN | 5% | In Progress | 100% |  |  |  |  | 5%
PRO18 | Testing18 | Adithya | Adithya | 2025-02-07 | 2025-03-07 | OPEN | 10% | Not Started | 100% |  |  |  |  | 10%
PRO18 | Internal signoff18 | Adithya | Adithya | 2025-02-07 | 2025-03-07 | OPEN | 2% | Not Started | 100% |  |  |  |  | 2%
PRO18 | customer signoff18 | Daniel | Adithya | 2025-02-07 | 2025-03-07 | OPEN | 3% | Not Started | 100% |  |  |  |  | 3%
PRO14 | CAN log file configuration | Sushmitha | Sachith | 2025-01-24 | 2025-01-29 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO2 | Printer | Manik | Mutturaman | 2024-11-29 | 2024-12-04 | CLOSED | 5% | completed | 100% |  |  |  |  | 5%
PRO3 | GUI Screen Modification | Manik | Sathya | 2024-12-24 | 2025-01-02 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO8 | Measurement data (Leak Testing) | Manik | Sushmitha | 2025-02-10 | 2025-02-17 | Open | 2% | In Progress | 100% |  |  |  |  | 2%
PRO16 | DIO Driver -F75111, Gen13 V and Gen 11 V | Anusha | Sachith | 2025-02-27 | 2025-03-06 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO16 | DIO Toolmonitor -F75111, Gen13 V and Gen 11 V | Anusha | Sachith | 2025-02-27 | 2025-03-03 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO3 | Feasa LED Analyser[RS232] | Anusha | Sathya | 2025-02-28 | 2025-03-01 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO3 | Report | Anusha | Sathya | 2025-02-28 | 2025-03-14 | CLOSED | 10% | Completed | 100% |  |  |  |  | 10%
PRO6 | Report | Anusha | Sachith | 2024-10-30 | 2024-11-26 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO6 | Can Flashed status Read driver | Anusha | Sachith | 2025-02-17 | 2025-03-19 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO6 | LCR | Anusha | Sachith | 2025-03-21 | 2025-03-25 | CLOSED | 5% | Completed | 100% |  |  |  |  | 5%
PRO19 | DMM | Pradeep | Sachith | 2025-03-07 | 2025-03-29 | OPEN | 50% | Not Started | 100% |  |  |  |  | 50%
PRO19 | Laser marking | Pradeep | Sachith | 2025-03-07 | 2025-03-29 | OPEN | 30% | Not Started | 100% |  |  |  |  | 30%
PRO19 | testing 19 | Pradeep | Sachith | 2025-03-07 | 2025-03-29 | OPEN | 15% | Not Started | 80% |  |  |  |  | 12%
PRO19 | Customer signoff 19 | Daniel | Sachith | 2025-03-07 | 2025-03-29 | OPEN | 5% | Not Started | 100% |  |  |  |  | 5%
PRO20 | Testing 20 Naxnova | Anusha | Sachith | 2025-03-07 | 2025-03-29 | Closed | 90% | Completed | 100% |  |  |  |  | 90%
PRO20 | Customer signoff 20 | Vithal | Sachith | 2025-03-07 | 2025-03-29 | Closed | 10% | Completed | 100% |  |  |  |  | 10%
PRO17 | Report | Anusha | Basavraj | 2025-03-17 | 2025-03-20 | CLOSED | 5% | Completed | 90% |  |  |  |  | 4.5%
PRO21 | Vision | Sunita | Annesh | 2025-03-07 | 2025-04-08 | Closed | 100% | Completed | 100% |  |  |  |  | 100%
PRO22 | Testing Indicator | Sunita | Annesh | 2025-05-01 | 2025-05-31 | In Progress | 100% | In Progress | 80% |  |  |  |  | 80%
PRO23 | Flash Programmer | Sreerag | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Flasher details, Flashing procedure, flashing files, bench setup | Vithal |  |  | 0.5%
PRO23 | CAN Transceiver | Sushmitha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | CAN details, bench setup | Vithal |  |  | 0.5%
PRO23 | Fixed Scanner | Anusha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Scanner command wrt model. Bench setup | Vithal |  |  | 0.25%
PRO23 | PPS | Sneha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO23 | DMM | Sneha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO23 | Function Generator | Prithvisha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO23 | Signal Generator | Prithvisha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Flasher details, Flashing procedure, flashing files, bench setup | Vithal |  |  | 0.5%
PRO23 | Multiplexer | Anusha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% |  | Vithal |  |  | 0.25%
PRO23 | Frequency Generator | Sushmitha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO23 | DC Electronic load | Sneha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.5%
PRO23 | Oscilloscope | Sushmitha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO23 | Printer | Anusha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Printer model make, ribbon, labels and content. | Vithal |  |  | 0.5%
PRO23 | SKIM | Anusha | Sachith | 2025-05-09 | 2025-06-28 | In Progress | 15% | Not Started | 5% |  | Vithal |  |  | 0.75%
PRO24 | CAN | Sneha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 15% | Not Started | 5% | CAN details, bench setup | Vithal |  |  | 0.75%
PRO24 | Camera | Pradeep | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% |  | Vithal |  |  | 0.5%
PRO24 | Spectrum Analyzer | Prithvisha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 15% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.75%
PRO24 | DMM | Sneha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.5%
PRO24 | PPS | Sneha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 15% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.75%
PRO24 | Laser Controller | Pradeep | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% |  | Vithal |  |  | 0.5%
PRO24 | Camera | Pradeep | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% |  | Vithal |  |  | 0.5%
PRO24 | Printer | Anusha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 15% | Not Started | 5% | Printer model make, ribbon, labels and content. | Vithal |  |  | 0.75%
PRO25 | Flash Programmer | Sushmitha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Flasher details, Flashing procedure, flashing files, bench setup | Vithal |  |  | 0.5%
PRO25 | DMM | Sneha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO25 | PPS | Sneha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO25 | Fixed Scanner | Anusha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Scanner command wrt model. Bench setup | Vithal |  |  | 0.5%
PRO25 | Multiplexer | Anusha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% |  | Vithal |  |  | 0.5%
PRO25 | Laser Controller | Pradeep | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% |  | Vithal |  |  | 0.5%
PRO25 | Fuction Generator | Sushmitha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Flasher details, Flashing procedure, flashing files, bench setup | Vithal |  |  | 0.5%
PRO25 | Signal Generator | Sushmitha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% | Flasher details, Flashing procedure, flashing files, bench setup | Vithal |  |  | 0.5%
PRO25 | UHF Receiver | Sneha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO25 | SKIM | Pradeep | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 10% | Not Started | 5% |  | Vithal |  |  | 0.5%
PRO25 | Spectrum Analyzer | Prithvisha | Annesh | 2025-05-09 | 2025-06-28 | In Progress | 5% | Not Started | 5% | Device details, communication protocol, bench setup | Vithal |  |  | 0.25%
PRO11 | MTS Generalization UI | Manik | Manik | 2025-05-14 | 2025-05-31 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | SCPI based Programmable Instruments | Sneha | Sneha | 2025-05-14 | 2025-05-31 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | Modbus | Sneha | Sneha | 2025-05-14 | 2025-05-21 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | CAN | Sneha | Sneha | 2025-05-14 | 2025-06-13 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | FLASHING | Sushmitha | Sushmitha | 2025-05-14 | 2025-05-27 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | Report | Anusha | Anusha | 2025-05-14 | 2025-05-26 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | Printer | Anusha | Anusha | 2025-05-14 | 2025-05-31 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | RS-232 | Anusha | Anusha | 2025-05-14 | 2025-07-15 | OPEN | 10% | In Progress | 100% |  |  |  |  | 10%
PRO11 | Calculations | Sneha | Basavaraj | 2025-05-14 | 2025-05-29 | Unit Test | 5% | In Progress | 100% |  |  |  |  | 5%
PRO11 | tcp/ip | Sneha | Sneha | 2025-05-14 | 2025-05-21 | OPEN | 5% | In Progress | 100% |  |  |  |  | 5%
PRO18 | Soldering Machine | Sushmitha | Adithya | 2025-05-20 | 2025-05-21 | Closed | 10% | Completed | 100% |  |  |  |  | 10%
PRO27 | PPS | Sneha | Annesh | 2025-06-25 | 2025-07-31 | OPEN | 20% | Not Started | 1% | Bench setup | Annesh | OPEN |  | 0.2%
PRO27 | Digital Power Meter | Prithvisha | Annesh | 2025-06-25 | 2025-07-31 | OPEN | 20% | Not Started | 1% |  |  |  |  | 0.2%
PRO27 | Oscilloscope | Sushmitha | Annesh | 2025-06-25 | 2025-07-31 | OPEN | 20% | Not Started | 1% | Bench setup | Annesh | OPEN |  | 0.2%
PRO27 | Flash Programmer | Sreerag | Annesh | 2025-06-25 | 2025-07-31 | OPEN | 20% | Not Started | 1% | Bench setup | Annesh | OPEN |  | 0.2%
PRO27 | Bluetooth Dongle | Anusha | Annesh | 2025-06-25 | 2025-07-31 | OPEN | 20% | Not Started | 1% | Bench setup | Annesh | OPEN |  | 0.2%
PRO28 | Vision | Sunita | Annesh | 2025-03-07 | 2025-04-08 | Closed | 100% | In Progress | 50% |  |  |  |  | 50%
PRO29 | Process traceability | Manik | Adithya | 2025-06-25 | 2025-08-09 | OPEN | 50% | Not Started | 10% | Master data and barcode details | Manik | OPEN |  | 5%
PRO29 | Part traceability | Manik | Adithya | 2025-06-25 | 2025-08-10 | OPEN | 50% | Not Started | 1% | childpart barcode details | Manik | OPEN |  | 0.5%
PRO25 | Dual screen UI | Venkat | Annesh | 2025-06-25 | 2025-07-12 | In Progress | 5% | Not Started | 5% |  |  |  |  | 0.25%
PRO25 | 3 screen UI | Manik | Annesh | 2025-06-25 | 2025-07-12 | In Progress | 5% | Not Started | 5% |  |  |  |  | 0.25%
PRO26 | CAN | Sneha | Annesh | 2025-06-02 | 2025-07-07 | Closed | 10% | completed | 100% |  |  |  |  | 10%
PRO26 | DMM | Prithvisha | Annesh | 2025-06-02 | 2025-07-07 | Closed | 10% | completed | 100% |  |  |  |  | 10%
PRO26 | PPS | Prithvisha | Annesh | 2025-06-02 | 2025-07-07 | Closed | 10% | completed | 100% |  |  |  |  | 10%
PRO26 | DC Electronic Load | Sushmitha | Annesh | 2025-06-02 | 2025-07-07 | Closed | 20% | completed | 100% |  |  |  |  | 20%
PRO26 | Fixed Scanner | Venkat | Annesh | 2025-06-02 | 2025-07-07 | In Progress | 10% | in Progress | 80% |  |  |  |  | 8%
PRO26 | MTS Test manager changes | Pradeep | Annesh | 2025-06-02 | 2025-07-07 | In Progress | 20% | in Progress | 5% |  |  |  |  | 1%
PRO26 | MTS Reports(MSA1,MSA3) | Sreerag | Annesh | 2025-06-02 | 2025-07-07 | In Progress | 10% | in Progress | 5% |  |  |  |  | 0.5%
PRO26 | Printer | Anusha | Annesh | 2025-06-02 | 2025-07-03 | In Progress | 10% | in Progress | 30% |  |  |  |  | 3%
Formulas:
Start Date = [End Date, row above]
End Date = [End Date, row below]-5
End Date = [Start Date]+10

## Projects
ProjectID | Project Name | Customer | Start date | End date | Overall Status | Project Health | Maintenance Project Name
PRO1 | Kirby Smart Device | Kirby | 2024-09-02 | 2024-11-15 | Cancelled | Green
PRO2 | EOL For Capacitive Touch Snake Sensor | NAXNOVA | 2024-09-02 | 2024-10-31 | Completed | Green
PRO3 | ICT for Pluggable Residual and Current Detector | Avalon | 2024-09-02 | 2025-03-30 | Completed | Green
PRO4 | On Board Charger Hella | HELLA | 2024-09-02 | 2025-03-30 | In Progress | Red
PRO5 | EOL Tester for Instrument cluster-Indication instrument | Indication Instruments | 2024-09-02 | 2025-04-10 | Completed | Green | 1
PRO6 | Avalon OBC And DTU | Avalon | 2024-09-02 | 2025-04-19 | Completed | Green
PRO7 | Assembly line for ECU -west port -syrma | Syrma -westport | 2024-09-02 | 2024-11-27 | Completed | Green
PRO8 | Yazaki Traceability | Yazaki | 2024-07-01 | 2025-03-30 | Completed | Green
PRO9 | Assembly line for OBC 3.3KW | Minda | 2024-10-14 | 2025-04-30 | In Progress | Green
PRO10 | Grading Machine for MOSFET | Turntide | 2024-10-14 | 2025-04-30 | Completed | Amber
PRO12 | MTS Vision | Micrologic | 2024-10-10 | 2025-01-31 | In Progress | Amber
PRO11 | MTS | Micrologic | 2024-10-10 | 2025-01-31 | In Progress | Amber
PRO13 | EOL For Wireless Chargeing Module(WCM) | Minda | 2024-11-13 | 2025-04-30 | Completed | Amber
PRO14 | EOL for 48V MCU | Mahindra | 2024-11-13 | 2025-03-30 | Completed | Green
PRO15 | Keypad inspection | Silky | 2024-11-11 | 2024-11-30 | Completed | Green | 1
PRO16 | Yazaki Traceability(Line2,Line3&Line4) | Yazaki | 2024-12-02 | 2025-03-30 | Completed | Green
PRO17 | FTM for WCM | Minda-Katolec | 2024-12-26 | 2025-04-30 | Completed | Amber
PRO18 | MCU Existing Line Traceability | Turntide | 2025-02-05 | 2025-04-30 | Completed | Amber
PRO19 | USB Charger | Yazaki | 2025-03-06 | 2025-04-30 | In Progress | Amber | 1
PRO20 | EOL For Capacitive Touch Snake Sensor(Additional variant) | NAXNOVA | 2025-03-07 | 2025-04-15 | Completed | Green
PRO21 | River Rider | Suprajith | 2025-03-07 | 2025-04-08 | Completed | Green
PRO22 | Indicator testing | Honda | 2025-04-29 | 2025-05-31 | In Progress | Red
PRO23 | BCON1_CONTROLLER | Lumax | 2025-05-09 | 2025-06-28 | In Progress | Red
PRO24 | BCON2_SWITCH | Lumax | 2025-05-09 | 2025-06-28 | In Progress | Red
PRO25 | BCON3_Key | Lumax | 2025-05-09 | 2025-06-28 | In Progress | Red
PRO26 | Functional Tester for VCU PCBA | Syrma | 2025-05-14 | 2025-06-21 | In Progress | Red
PRO27 | Integrated Outdoor Luminaire Controller | Signify | 2025-06-16 | 2025-08-30 | Not Started | Red
PRO28 | River Rider 1 | Suprajith | 2025-06-23 | 2025-08-04 | Not Started | Amber
PRO29 | Assembly line for Infotainment System | Panasonic Automotive | 2025-06-23 | 2025-08-25 | Not Started | Red

## Projects1
ProjectID | Project Name | Customer | Start date | End date | Overall Status | Project Health
PRO1 | Kirby Smart Device | Kirby | 2024-09-02 | 2024-11-15 | Cancelled | Red
PRO2 | EOL For Capacitive Touch Snake Sensor | NAXNOVA | 2024-09-02 | 2024-10-31 | In Progress | Green
PRO3 | ICT for Pluggable Residual and Current Detector | Avalon | 2024-09-02 | 2024-12-25 | In Progress | Amber
PRO4 | On Board Charger Hella | HELLA | 2024-09-02 | 2024-12-07 | on Hold | Red
PRO5 | EOL Tester for Instrument cluster-Indication instrument | Indication Instruments | 2024-09-02 | 2024-11-30 | In Progress | Green
PRO6 | Avalon OBC And DTU | Avalon | 2024-09-02 | 2024-11-30 | In Progress | Amber
PRO7 | Assembly line for ECU -west port -syrma | Syrma -westport | 2024-09-02 | 2024-11-27 | In Progress | Green
PRO8 | Yazaki Traceability | Yazaki | 2024-07-01 | 2024-10-31 | In Progress | Green
PRO9 | Assembly line for OBC 3.3KW | Minda | 2024-10-14 | 2025-01-07 | Not started | Red
PRO10 | Grading Machine for MOSFET | Turntide | 2024-10-14 | 2025-01-10 | Not started | Red
PRO12 | MTS Vision | Micrologic | 2024-10-10 | 2025-01-31 | In Progress | Red
PRO11 | MTS | Micrologic | 2024-10-10 | 2025-01-31 | In Progress | Red
PRO13 | EOL For Wireless charger | Minda | 2024-11-13 | 2024-12-16 | Not started | Red
PRO14 | EOL for 48V MCU | Mahindra | 2024-11-13 | 2024-12-20 | Not started | Red
PRO15 | Keypad inspection | Silky | 2024-11-11 | 2024-11-30 | In Progress | Red
PRO16 | Yazaki Traceability(Line2&Line3) | Yazaki | 2024-12-04 | 2024-12-20 | Not started | Red

## CustomerFeedback
ProjectID | Project Name | Owner | Activities | Issue Description | Solution Description | Customer feedback | Status
PRO13 | EOL For Wireless Chargeing Module(WCM) | Pradeep | Duplicate serial number generation | Barcode with same content is generated and printed. | Now before printing barcode it will check if the data with same barcode is present in db or not. If present it will not print. if not present it will print | ok | closed

## Activity Status
Sl No | Date | Activity Status | Status Count
1 | 2024-10-07 | OPEN | 56
2 | 2024-10-07 | CLOSED | 16
3 | 2024-10-07 | On Hold | 3
4 | 2024-10-08 | OPEN | 56
5 | 2024-10-08 | On Hold | 3
6 | 2024-10-08 | CLOSED | 16
7 | 2024-10-08 | On Hold | 3
8 | 2024-10-08 | OPEN | 54
9 | 2024-10-08 | CLOSED | 18
10 | 2024-10-09 | CLOSED | 16
11 | 2024-10-09 | On Hold | 3
12 | 2024-10-09 | OPEN | 56
13 | 2024-10-10 | On Hold | 3
14 | 2024-10-10 | CLOSED | 16
15 | 2024-10-10 | OPEN | 57
16 | 2024-10-11 | CLOSED | 16
17 | 2024-10-11 | On Hold | 3
18 | 2024-10-11 | OPEN | 57
19 | 2024-10-12 | CLOSED | 16
20 | 2024-10-12 | On Hold | 3
21 | 2024-10-12 | OPEN | 57
22 | 2024-10-13 | OPEN | 57
23 | 2024-10-13 | On Hold | 3
24 | 2024-10-13 | CLOSED | 16
25 | 2024-10-14 | CLOSED | 16
26 | 2024-10-14 | On Hold | 3
27 | 2024-10-14 | OPEN | 57
28 | 2024-10-15 | OPEN | 56
29 | 2024-10-15 | On Hold | 2
30 | 2024-10-15 | CLOSED | 18
31 | 2024-10-16 | On Hold | 2
32 | 2024-10-16 | CLOSED | 18
33 | 2024-10-16 | OPEN | 58
34 | 2024-10-17 | CLOSED | 19
35 | 2024-10-17 | On Hold | 1
36 | 2024-10-17 | OPEN | 58
37 | 2024-10-18 | CLOSED | 19
38 | 2024-10-18 | On Hold | 1
39 | 2024-10-18 | OPEN | 83
40 | 2024-10-19 | OPEN | 83
41 | 2024-10-19 | On Hold | 1
42 | 2024-10-19 | CLOSED | 19
43 | 2024-10-20 | On Hold | 1
44 | 2024-10-20 | OPEN | 83
45 | 2024-10-20 | CLOSED | 19
46 | 2024-10-21 | On Hold | 7
47 | 2024-10-21 | OPEN | 77
48 | 2024-10-21 | CLOSED | 19
49 | 2024-10-22 | CLOSED | 19
50 | 2024-10-22 | OPEN | 77
51 | 2024-10-22 | On Hold | 7
52 | 2024-10-23 | On Hold | 7
53 | 2024-10-23 | CLOSED | 18
54 | 2024-10-23 | OPEN | 79
55 | 2024-10-24 | CLOSED | 18
56 | 2024-10-24 | On Hold | 7
57 | 2024-10-24 | OPEN | 79
58 | 2024-10-25 | CLOSED | 19
59 | 2024-10-25 | OPEN | 95
60 | 2024-10-25 | On Hold | 7
61 | 2024-11-04 | On Hold | 6
62 | 2024-11-04 | OPEN | 96
63 | 2024-11-04 | CLOSED | 19
64 | 2024-11-05 | CLOSED | 19
65 | 2024-11-05 | On Hold | 6
66 | 2024-11-05 | OPEN | 96
67 | 2024-11-06 | On Hold | 6
68 | 2024-11-06 | OPEN | 96
69 | 2024-11-06 | CLOSED | 20
70 | 2024-11-07 | On Hold | 6
71 | 2024-11-07 | CLOSED | 20
72 | 2024-11-07 | OPEN | 96
73 | 2024-11-08 | OPEN | 98
74 | 2024-11-08 | CLOSED | 20
75 | 2024-11-08 | On Hold | 6
76 | 2024-11-09 | OPEN | 71
77 | 2024-11-09 | CLOSED | 20
78 | 2024-11-09 | On Hold | 31
79 | 2024-11-10 | CLOSED | 21
80 | 2024-11-10 | OPEN | 71
81 | 2024-11-10 | On Hold | 31
82 | 2024-11-11 | CLOSED | 21
83 | 2024-11-11 | On Hold | 30
84 | 2024-11-11 | OPEN | 71
85 | 2024-11-12 | OPEN | 71
86 | 2024-11-12 | CLOSED | 21
87 | 2024-11-12 | On Hold | 30
88 | 2024-11-13 | CLOSED | 21
89 | 2024-11-13 | OPEN | 71
90 | 2024-11-13 | On Hold | 30
91 | 2024-11-14 | OPEN | 93
92 | 2024-11-14 | CLOSED | 21
93 | 2024-11-14 | On Hold | 30
94 | 2024-11-15 | On Hold | 30
95 | 2024-11-15 | CLOSED | 21
96 | 2024-11-15 | OPEN | 93
97 | 2024-11-16 | On Hold | 30
98 | 2024-11-16 | CLOSED | 21
99 | 2024-11-16 | OPEN | 93
100 | 2024-11-17 | OPEN | 93
101 | 2024-11-17 | On Hold | 30
102 | 2024-11-17 | CLOSED | 21
103 | 2024-11-18 | OPEN | 93
104 | 2024-11-18 | On Hold | 30
105 | 2024-11-18 | CLOSED | 21
106 | 2024-11-19 | On Hold | 30
107 | 2024-11-19 | CLOSED | 21
108 | 2024-11-19 | OPEN | 93
109 | 2024-11-20 | OPEN | 93
110 | 2024-11-20 | CLOSED | 21
111 | 2024-11-20 | On Hold | 30
112 | 2024-11-21 | CLOSED | 21
113 | 2024-11-21 | OPEN | 93
114 | 2024-11-21 | On Hold | 30
115 | 2024-11-22 | CLOSED | 21
116 | 2024-11-22 | On Hold | 30
117 | 2024-11-22 | OPEN | 93
118 | 2024-11-23 | On Hold | 23
119 | 2024-11-23 | OPEN | 87
120 | 2024-11-23 | CLOSED | 21
121 | 2024-11-24 | CLOSED | 23
122 | 2024-11-24 | OPEN | 85
123 | 2024-11-24 | On Hold | 23
124 | 2024-11-25 | On Hold | 23
125 | 2024-11-25 | CLOSED | 23
126 | 2024-11-25 | OPEN | 85
127 | 2024-11-26 | CLOSED | 24
128 | 2024-11-26 | OPEN | 84
129 | 2024-11-26 | On Hold | 23
130 | 2024-11-27 | CLOSED | 24
131 | 2024-11-27 | On Hold | 39
132 | 2024-11-27 | OPEN | 76
133 | 2024-11-28 | CLOSED | 24
134 | 2024-11-28 | OPEN | 78
135 | 2024-11-28 | On Hold | 39
136 | 2024-11-29 | On Hold | 39
137 | 2024-11-29 | OPEN | 78
138 | 2024-11-29 | CLOSED | 24
139 | 2024-11-30 | CLOSED | 24
140 | 2024-11-30 | On Hold | 38
141 | 2024-11-30 | OPEN | 80
142 | 2024-12-01 | CLOSED | 24
143 | 2024-12-01 | OPEN | 80
144 | 2024-12-01 | On Hold | 38
145 | 2024-12-02 | CLOSED | 24
146 | 2024-12-02 | On Hold | 38
147 | 2024-12-02 | OPEN | 81
148 | 2024-12-03 | On Hold | 38
149 | 2024-12-03 | CLOSED | 26
150 | 2024-12-03 | OPEN | 79
151 | 2024-12-04 | CLOSED | 26
152 | 2024-12-04 | OPEN | 79
153 | 2024-12-04 | On Hold | 38
154 | 2024-12-05 | On Hold | 46
155 | 2024-12-05 | OPEN | 72
156 | 2024-12-05 | CLOSED | 26
157 | 2024-12-06 | CLOSED | 26
158 | 2024-12-06 | OPEN | 73
159 | 2024-12-06 | On Hold | 46
160 | 2024-12-07 | OPEN | 73
161 | 2024-12-07 | On Hold | 46
162 | 2024-12-07 | CLOSED | 26
163 | 2024-12-08 | OPEN | 72
164 | 2024-12-08 | On Hold | 46
165 | 2024-12-08 | CLOSED | 27
166 | 2024-12-09 | OPEN | 74
167 | 2024-12-09 | CLOSED | 27
168 | 2024-12-09 | On Hold | 46
169 | 2024-12-10 | CLOSED | 27
170 | 2024-12-10 | OPEN | 75
171 | 2024-12-10 | On Hold | 45
172 | 2024-12-11 | CLOSED | 27
173 | 2024-12-11 | On Hold | 45
174 | 2024-12-11 | OPEN | 75
175 | 2024-12-12 | On Hold | 45
176 | 2024-12-12 | OPEN | 75
177 | 2024-12-12 | CLOSED | 27
178 | 2024-12-13 | OPEN | 75
179 | 2024-12-13 | CLOSED | 27
180 | 2024-12-13 | On Hold | 45
181 | 2024-12-14 | CLOSED | 29
182 | 2024-12-14 | OPEN | 75
183 | 2024-12-14 | On Hold | 44
184 | 2024-12-15 | OPEN | 75
185 | 2024-12-15 | CLOSED | 29
186 | 2024-12-15 | On Hold | 44
187 | 2024-12-16 | On Hold | 35
188 | 2024-12-16 | CLOSED | 27
189 | 2024-12-16 | OPEN | 89
190 | 2024-12-17 | CLOSED | 27
191 | 2024-12-17 | On Hold | 35
192 | 2024-12-17 | OPEN | 89
193 | 2024-12-18 | CLOSED | 27
194 | 2024-12-18 | OPEN | 89
195 | 2024-12-18 | On Hold | 35
196 | 2024-12-19 | CLOSED | 29
197 | 2024-12-19 | OPEN | 89
198 | 2024-12-19 | On Hold | 34
199 | 2024-12-20 | On Hold | 34
200 | 2024-12-20 | CLOSED | 29
201 | 2024-12-20 | OPEN | 89
202 | 2024-12-21 | OPEN | 89
203 | 2024-12-21 | On Hold | 34
204 | 2024-12-21 | CLOSED | 29
205 | 2024-12-22 | CLOSED | 29
206 | 2024-12-22 | OPEN | 89
207 | 2024-12-22 | On Hold | 34
208 | 2024-12-23 | OPEN | 89
209 | 2024-12-23 | CLOSED | 29
210 | 2024-12-23 | On Hold | 34
211 | 2024-12-24 | On Hold | 34
212 | 2024-12-24 | OPEN | 89
213 | 2024-12-24 | CLOSED | 29
214 | 2024-12-25 | CLOSED | 29
215 | 2024-12-25 | On Hold | 34
216 | 2024-12-25 | OPEN | 91
217 | 2024-12-26 | CLOSED | 29
218 | 2024-12-26 | On Hold | 34
219 | 2024-12-26 | OPEN | 91
220 | 2024-12-27 | On Hold | 34
221 | 2024-12-27 | CLOSED | 29
222 | 2024-12-27 | OPEN | 91
223 | 2024-12-28 | On Hold | 34
224 | 2024-12-28 | OPEN | 91
225 | 2024-12-28 | CLOSED | 29
226 | 2024-12-29 | CLOSED | 29
227 | 2024-12-29 | OPEN | 91
228 | 2024-12-29 | On Hold | 34
229 | 2024-12-30 | On Hold | 34
230 | 2024-12-30 | OPEN | 91
231 | 2024-12-30 | CLOSED | 29
232 | 2024-12-31 | CLOSED | 29
233 | 2024-12-31 | On Hold | 34
234 | 2024-12-31 | OPEN | 91
235 | 2025-01-01 | On Hold | 34
236 | 2025-01-01 | OPEN | 91
237 | 2025-01-01 | CLOSED | 29
238 | 2025-01-02 | On Hold | 34
239 | 2025-01-02 | OPEN | 91
240 | 2025-01-02 | CLOSED | 29
241 | 2025-01-03 | On Hold | 34
242 | 2025-01-03 | CLOSED | 30
243 | 2025-01-03 | OPEN | 91
244 | 2025-01-04 | OPEN | 91
245 | 2025-01-04 | CLOSED | 30
246 | 2025-01-04 | On Hold | 34
247 | 2025-01-05 | CLOSED | 30
248 | 2025-01-05 | OPEN | 91
249 | 2025-01-05 | On Hold | 34
250 | 2025-01-06 | CLOSED | 30
251 | 2025-01-06 | OPEN | 92
252 | 2025-01-06 | On Hold | 34
253 | 2025-01-07 | On Hold | 35
254 | 2025-01-07 | OPEN | 91
255 | 2025-01-07 | CLOSED | 30
256 | 2025-01-08 | OPEN | 91
257 | 2025-01-08 | On Hold | 35
258 | 2025-01-08 | CLOSED | 30
259 | 2025-01-09 | OPEN | 91
260 | 2025-01-09 | CLOSED | 36
261 | 2025-01-09 | On Hold | 29
262 | 2025-01-10 | On Hold | 29
263 | 2025-01-10 | CLOSED | 44
264 | 2025-01-10 | OPEN | 83
265 | 2025-01-11 | OPEN | 81
266 | 2025-01-11 | On Hold | 29
267 | 2025-01-11 | CLOSED | 46
268 | 2025-01-12 | CLOSED | 46
269 | 2025-01-12 | OPEN | 81
270 | 2025-01-12 | On Hold | 29
271 | 2025-01-13 | OPEN | 81
272 | 2025-01-13 | CLOSED | 46
273 | 2025-01-13 | On Hold | 29
274 | 2025-01-14 | CLOSED | 46
275 | 2025-01-14 | On Hold | 29
276 | 2025-01-14 | OPEN | 81
277 | 2025-01-15 | OPEN | 81
278 | 2025-01-15 | CLOSED | 46
279 | 2025-01-15 | On Hold | 29
280 | 2025-01-16 | On Hold | 28
281 | 2025-01-16 | CLOSED | 60
282 | 2025-01-16 | OPEN | 77
283 | 2025-01-17 | On Hold | 28
284 | 2025-01-17 | CLOSED | 60
285 | 2025-01-17 | OPEN | 78
286 | 2025-01-18 | OPEN | 78
287 | 2025-01-18 | CLOSED | 60
288 | 2025-01-18 | On Hold | 28
289 | 2025-01-19 | OPEN | 78
290 | 2025-01-19 | CLOSED | 60
291 | 2025-01-19 | On Hold | 28
292 | 2025-01-20 | OPEN | 78
293 | 2025-01-20 | On Hold | 28
294 | 2025-01-20 | CLOSED | 60
295 | 2025-01-21 | OPEN | 78
296 | 2025-01-21 | CLOSED | 60
297 | 2025-01-21 | On Hold | 28
298 | 2025-01-22 | CLOSED | 60
299 | 2025-01-22 | On Hold | 28
300 | 2025-01-22 | OPEN | 78
301 | 2025-01-23 | CLOSED | 60
302 | 2025-01-23 | OPEN | 79
303 | 2025-01-23 | On Hold | 28
304 | 2025-01-24 | CLOSED | 60
305 | 2025-01-24 | OPEN | 79
306 | 2025-01-24 | On Hold | 28
307 | 2025-01-25 | On Hold | 28
308 | 2025-01-25 | CLOSED | 60
309 | 2025-01-25 | OPEN | 79
310 | 2025-01-26 | CLOSED | 60
311 | 2025-01-26 | On Hold | 28
312 | 2025-01-26 | OPEN | 79
313 | 2025-01-27 | CLOSED | 60
314 | 2025-01-27 | On Hold | 28
315 | 2025-01-27 | OPEN | 79
316 | 2025-01-28 | On Hold | 28
317 | 2025-01-28 | OPEN | 74
318 | 2025-01-28 | CLOSED | 66
319 | 2025-01-29 | OPEN | 53
320 | 2025-01-29 | On Hold | 28
321 | 2025-01-29 | CLOSED | 79
322 | 2025-01-30 | OPEN | 50
323 | 2025-01-30 | CLOSED | 85
324 | 2025-01-30 | On Hold | 30
325 | 2025-01-31 | OPEN | 50
326 | 2025-01-31 | On Hold | 30
327 | 2025-01-31 | CLOSED | 85
328 | 2025-02-01 | OPEN | 50
329 | 2025-02-01 | CLOSED | 85
330 | 2025-02-01 | On Hold | 30
331 | 2025-02-02 | OPEN | 50
332 | 2025-02-02 | CLOSED | 85
333 | 2025-02-02 | On Hold | 30
334 | 2025-02-03 | On Hold | 30
335 | 2025-02-03 | CLOSED | 85
336 | 2025-02-03 | OPEN | 50
337 | 2025-02-04 | CLOSED | 85
338 | 2025-02-04 | OPEN | 50
339 | 2025-02-04 | On Hold | 30
340 | 2025-02-05 | CLOSED | 85
341 | 2025-02-05 | On Hold | 30
342 | 2025-02-05 | OPEN | 50
343 | 2025-02-06 | OPEN | 50
344 | 2025-02-06 | On Hold | 30
345 | 2025-02-06 | CLOSED | 85
346 | 2025-02-07 | OPEN | 58
347 | 2025-02-07 | On Hold | 25
348 | 2025-02-07 | CLOSED | 91
349 | 2025-02-08 | On Hold | 22
350 | 2025-02-08 | CLOSED | 92
351 | 2025-02-08 | OPEN | 60
352 | 2025-02-09 | On Hold | 22
353 | 2025-02-09 | OPEN | 60
354 | 2025-02-09 | CLOSED | 92
355 | 2025-02-10 | OPEN | 57
356 | 2025-02-10 | CLOSED | 97
357 | 2025-02-10 | On Hold | 22
358 | 2025-02-11 | On Hold | 22
359 | 2025-02-11 | OPEN | 57
360 | 2025-02-11 | CLOSED | 97
361 | 2025-02-12 | CLOSED | 97
362 | 2025-02-12 | OPEN | 57
363 | 2025-02-12 | On Hold | 22
364 | 2025-02-13 | OPEN | 57
365 | 2025-02-13 | On Hold | 22
366 | 2025-02-13 | CLOSED | 97
367 | 2025-02-14 | CLOSED | 97
368 | 2025-02-14 | OPEN | 57
369 | 2025-02-14 | On Hold | 22
370 | 2025-02-15 | CLOSED | 97
371 | 2025-02-15 | On Hold | 22
372 | 2025-02-15 | OPEN | 57
373 | 2025-02-16 | CLOSED | 97
374 | 2025-02-16 | On Hold | 22
375 | 2025-02-16 | OPEN | 57
376 | 2025-02-17 | CLOSED | 97
377 | 2025-02-17 | OPEN | 57
378 | 2025-02-17 | On Hold | 22
379 | 2025-02-18 | OPEN | 57
380 | 2025-02-18 | On Hold | 22
381 | 2025-02-18 | CLOSED | 97
382 | 2025-02-19 | CLOSED | 97
383 | 2025-02-19 | OPEN | 57
384 | 2025-02-19 | On Hold | 22
385 | 2025-02-20 | On Hold | 22
386 | 2025-02-20 | OPEN | 56
387 | 2025-02-20 | CLOSED | 100
388 | 2025-02-21 | OPEN | 56
389 | 2025-02-21 | CLOSED | 100
390 | 2025-02-21 | On Hold | 22
391 | 2025-02-22 | On Hold | 22
392 | 2025-02-22 | OPEN | 56
393 | 2025-02-22 | CLOSED | 100
394 | 2025-02-23 | On Hold | 22
395 | 2025-02-23 | OPEN | 56
396 | 2025-02-23 | CLOSED | 100
397 | 2025-02-24 | OPEN | 56
398 | 2025-02-24 | CLOSED | 100
399 | 2025-02-24 | On Hold | 22
400 | 2025-02-25 | On Hold | 22
401 | 2025-02-25 | OPEN | 56
402 | 2025-02-25 | CLOSED | 100
403 | 2025-02-26 | CLOSED | 100
404 | 2025-02-26 | On Hold | 22
405 | 2025-02-26 | OPEN | 56
406 | 2025-02-27 | CLOSED | 100
407 | 2025-02-27 | On Hold | 22
408 | 2025-02-27 | OPEN | 56
409 | 2025-02-28 | On Hold | 22
410 | 2025-02-28 | CLOSED | 100
411 | 2025-02-28 | OPEN | 56
412 | 2025-03-01 | OPEN | 56
413 | 2025-03-01 | CLOSED | 100
414 | 2025-03-01 | On Hold | 22
415 | 2025-03-02 | OPEN | 56
416 | 2025-03-02 | On Hold | 22
417 | 2025-03-02 | CLOSED | 100
418 | 2025-03-03 | On Hold | 22
419 | 2025-03-03 | OPEN | 56
420 | 2025-03-03 | CLOSED | 100
421 | 2025-03-04 | OPEN | 57
422 | 2025-03-04 | On Hold | 22
423 | 2025-03-04 | CLOSED | 102
424 | 2025-03-05 | OPEN | 57
425 | 2025-03-05 | On Hold | 22
426 | 2025-03-05 | CLOSED | 102
427 | 2025-03-06 | On Hold | 22
428 | 2025-03-06 | CLOSED | 102
429 | 2025-03-06 | OPEN | 57
430 | 2025-03-07 | OPEN | 57
431 | 2025-03-07 | CLOSED | 105
432 | 2025-03-07 | On Hold | 23
433 | 2025-03-08 | On Hold | 23
434 | 2025-03-08 | OPEN | 57
435 | 2025-03-08 | CLOSED | 105
436 | 2025-03-09 | On Hold | 23
437 | 2025-03-09 | OPEN | 57
438 | 2025-03-09 | CLOSED | 105
439 | 2025-03-10 | On Hold | 23
440 | 2025-03-10 | CLOSED | 105
441 | 2025-03-10 | OPEN | 57
442 | 2025-03-11 | CLOSED | 105
443 | 2025-03-11 | On Hold | 23
444 | 2025-03-11 | OPEN | 57
445 | 2025-03-12 | On Hold | 23
446 | 2025-03-12 | OPEN | 57
447 | 2025-03-12 | CLOSED | 105
448 | 2025-03-13 | On Hold | 23
449 | 2025-03-13 | OPEN | 57
450 | 2025-03-13 | CLOSED | 105
451 | 2025-03-14 | On Hold | 23
452 | 2025-03-14 | OPEN | 57
453 | 2025-03-14 | CLOSED | 105
454 | 2025-03-15 | OPEN | 57
455 | 2025-03-15 | On Hold | 23
456 | 2025-03-15 | CLOSED | 105
457 | 2025-03-16 | OPEN | 57
458 | 2025-03-16 | CLOSED | 105
459 | 2025-03-16 | On Hold | 23
460 | 2025-03-17 | OPEN | 57
461 | 2025-03-17 | On Hold | 23
462 | 2025-03-17 | CLOSED | 105
463 | 2025-03-18 | OPEN | 61
464 | 2025-03-18 | CLOSED | 109
465 | 2025-03-18 | On Hold | 24
466 | 2025-03-19 | On Hold | 24
467 | 2025-03-19 | OPEN | 61
468 | 2025-03-19 | CLOSED | 109
469 | 2025-03-20 | CLOSED | 109
470 | 2025-03-20 | On Hold | 24
471 | 2025-03-20 | OPEN | 61
472 | 2025-03-21 | On Hold | 24
473 | 2025-03-21 | CLOSED | 109
474 | 2025-03-21 | OPEN | 61
475 | 2025-03-22 | On Hold | 24
476 | 2025-03-22 | CLOSED | 109
477 | 2025-03-22 | OPEN | 61
478 | 2025-03-23 | CLOSED | 109
479 | 2025-03-23 | On Hold | 24
480 | 2025-03-23 | OPEN | 61
481 | 2025-03-24 | CLOSED | 109
482 | 2025-03-24 | OPEN | 61
483 | 2025-03-24 | On Hold | 24
484 | 2025-03-25 | On Hold | 23
485 | 2025-03-25 | OPEN | 60
486 | 2025-03-25 | CLOSED | 111
487 | 2025-03-26 | CLOSED | 111
488 | 2025-03-26 | OPEN | 60
489 | 2025-03-26 | On Hold | 23
490 | 2025-03-27 | On Hold | 23
491 | 2025-03-27 | OPEN | 60
492 | 2025-03-27 | CLOSED | 111
493 | 2025-03-28 | OPEN | 60
494 | 2025-03-28 | On Hold | 23
495 | 2025-03-28 | CLOSED | 111
496 | 2025-03-29 | OPEN | 60
497 | 2025-03-29 | On Hold | 23
498 | 2025-03-29 | CLOSED | 111
499 | 2025-03-30 | On Hold | 23
500 | 2025-03-30 | OPEN | 49
501 | 2025-03-30 | CLOSED | 122
502 | 2025-03-31 | CLOSED | 122
503 | 2025-03-31 | OPEN | 49
504 | 2025-03-31 | On Hold | 23
505 | 2025-04-01 | On Hold | 23
506 | 2025-04-01 | OPEN | 49
507 | 2025-04-01 | CLOSED | 122
508 | 2025-04-02 | CLOSED | 122
509 | 2025-04-02 | OPEN | 49
510 | 2025-04-02 | On Hold | 23
511 | 2025-04-03 | On Hold | 23
512 | 2025-04-03 | CLOSED | 122
513 | 2025-04-03 | OPEN | 49
514 | 2025-04-04 | On Hold | 23
515 | 2025-04-04 | OPEN | 49
516 | 2025-04-04 | CLOSED | 122
517 | 2025-04-05 | On Hold | 23
518 | 2025-04-05 | OPEN | 49
519 | 2025-04-05 | CLOSED | 122
520 | 2025-04-06 | OPEN | 49
521 | 2025-04-06 | CLOSED | 122
522 | 2025-04-06 | On Hold | 23
523 | 2025-04-07 | On Hold | 23
524 | 2025-04-07 | OPEN | 49
525 | 2025-04-07 | CLOSED | 122
526 | 2025-04-08 | OPEN | 49
527 | 2025-04-08 | CLOSED | 122
528 | 2025-04-08 | On Hold | 23
529 | 2025-04-09 | On Hold | 23
530 | 2025-04-09 | CLOSED | 122
531 | 2025-04-09 | OPEN | 49
532 | 2025-04-10 | CLOSED | 122
533 | 2025-04-10 | OPEN | 49
534 | 2025-04-10 | On Hold | 23
535 | 2025-04-11 | On Hold | 23
536 | 2025-04-11 | CLOSED | 122
537 | 2025-04-11 | OPEN | 49
538 | 2025-04-12 | CLOSED | 122
539 | 2025-04-12 | On Hold | 23
540 | 2025-04-12 | OPEN | 49
541 | 2025-04-13 | On Hold | 23
542 | 2025-04-13 | CLOSED | 122
543 | 2025-04-13 | OPEN | 49
544 | 2025-04-14 | On Hold | 22
545 | 2025-04-14 | OPEN | 49
546 | 2025-04-14 | CLOSED | 123
547 | 2025-04-15 | CLOSED | 123
548 | 2025-04-15 | On Hold | 22
549 | 2025-04-15 | OPEN | 49
550 | 2025-04-16 | CLOSED | 123
551 | 2025-04-16 | On Hold | 22
552 | 2025-04-16 | OPEN | 49
553 | 2025-04-17 | On Hold | 22
554 | 2025-04-17 | OPEN | 49
555 | 2025-04-17 | CLOSED | 123
556 | 2025-04-18 | On Hold | 22
557 | 2025-04-18 | CLOSED | 123
558 | 2025-04-18 | OPEN | 49
559 | 2025-04-19 | OPEN | 49
560 | 2025-04-19 | On Hold | 22
561 | 2025-04-19 | CLOSED | 123
562 | 2025-04-20 | OPEN | 49
563 | 2025-04-20 | On Hold | 22
564 | 2025-04-20 | CLOSED | 123
565 | 2025-04-21 | OPEN | 49
566 | 2025-04-21 | CLOSED | 123
567 | 2025-04-21 | On Hold | 22
568 | 2025-04-22 | OPEN | 44
569 | 2025-04-22 | CLOSED | 126
570 | 2025-04-22 | On Hold | 22
571 | 2025-04-23 | CLOSED | 126
572 | 2025-04-23 | OPEN | 44
573 | 2025-04-23 | On Hold | 22
574 | 2025-04-24 | OPEN | 44
575 | 2025-04-24 | On Hold | 22
576 | 2025-04-24 | CLOSED | 126
577 | 2025-04-25 | On Hold | 22
578 | 2025-04-25 | CLOSED | 126
579 | 2025-04-25 | OPEN | 44
580 | 2025-04-26 | On Hold | 22
581 | 2025-04-26 | CLOSED | 126
582 | 2025-04-26 | OPEN | 44
583 | 2025-04-27 | On Hold | 22
584 | 2025-04-27 | CLOSED | 126
585 | 2025-04-27 | OPEN | 44
586 | 2025-04-28 | CLOSED | 126
587 | 2025-04-28 | On Hold | 22
588 | 2025-04-28 | OPEN | 44
589 | 2025-04-29 | On Hold | 22
590 | 2025-04-29 | OPEN | 44
591 | 2025-04-29 | CLOSED | 126
592 | 2025-04-30 | OPEN | 44
593 | 2025-04-30 | CLOSED | 126
594 | 2025-04-30 | On Hold | 22
595 | 2025-05-01 | OPEN | 44
596 | 2025-05-01 | On Hold | 22
597 | 2025-05-01 | CLOSED | 126
598 | 2025-05-02 | OPEN | 44
599 | 2025-05-02 | CLOSED | 126
600 | 2025-05-02 | On Hold | 22
601 | 2025-05-03 | OPEN | 44
602 | 2025-05-03 | On Hold | 22
603 | 2025-05-03 | CLOSED | 126
604 | 2025-05-04 | On Hold | 22
605 | 2025-05-04 | CLOSED | 126
606 | 2025-05-04 | OPEN | 44
607 | 2025-05-05 | OPEN | 44
608 | 2025-05-05 | CLOSED | 126
609 | 2025-05-05 | On Hold | 22
610 | 2025-05-06 | On Hold | 22
611 | 2025-05-06 | OPEN | 44
612 | 2025-05-06 | CLOSED | 126
613 | 2025-05-07 | CLOSED | 126
614 | 2025-05-07 | OPEN | 44
615 | 2025-05-07 | On Hold | 22
616 | 2025-05-08 | On Hold | 22
617 | 2025-05-08 | CLOSED | 126
618 | 2025-05-08 | OPEN | 44
619 | 2025-05-09 | OPEN | 44
620 | 2025-05-09 | On Hold | 22
621 | 2025-05-09 | CLOSED | 126
622 | 2025-05-10 | On Hold | 22
623 | 2025-05-10 | CLOSED | 126
624 | 2025-05-10 | OPEN | 44
625 | 2025-05-11 | On Hold | 22
626 | 2025-05-11 | OPEN | 44
627 | 2025-05-11 | CLOSED | 126
628 | 2025-05-12 | OPEN | 44
629 | 2025-05-12 | On Hold | 22
630 | 2025-05-12 | CLOSED | 126
631 | 2025-05-13 | On Hold | 20
632 | 2025-05-13 | OPEN | 40
633 | 2025-05-13 | CLOSED | 132
634 | 2025-05-14 | CLOSED | 132
635 | 2025-05-14 | OPEN | 40
636 | 2025-05-14 | On Hold | 20
637 | 2025-05-15 | On Hold | 20
638 | 2025-05-15 | OPEN | 50
639 | 2025-05-15 | CLOSED | 131
640 | 2025-05-16 | On Hold | 20
641 | 2025-05-16 | OPEN | 50
642 | 2025-05-16 | CLOSED | 131
643 | 2025-05-17 | On Hold | 20
644 | 2025-05-17 | OPEN | 50
645 | 2025-05-17 | CLOSED | 131
646 | 2025-05-18 | On Hold | 20
647 | 2025-05-18 | CLOSED | 131
648 | 2025-05-18 | OPEN | 50
649 | 2025-05-19 | CLOSED | 131
650 | 2025-05-19 | On Hold | 20
651 | 2025-05-19 | OPEN | 50
652 | 2025-05-20 | CLOSED | 131
653 | 2025-05-20 | OPEN | 49
654 | 2025-05-20 | On Hold | 20
655 | 2025-05-21 | On Hold | 20
656 | 2025-05-21 | CLOSED | 131
657 | 2025-05-21 | OPEN | 49
658 | 2025-05-22 | On Hold | 20
659 | 2025-05-22 | CLOSED | 131
660 | 2025-05-22 | OPEN | 49
661 | 2025-05-23 | CLOSED | 131
662 | 2025-05-23 | On Hold | 20
663 | 2025-05-23 | OPEN | 49
664 | 2025-05-24 | On Hold | 20
665 | 2025-05-24 | OPEN | 49
666 | 2025-05-24 | CLOSED | 131
667 | 2025-05-25 | On Hold | 20
668 | 2025-05-25 | OPEN | 49
669 | 2025-05-25 | CLOSED | 131
670 | 2025-05-26 | On Hold | 20
671 | 2025-05-26 | CLOSED | 131
672 | 2025-05-26 | OPEN | 49
673 | 2025-05-27 | On Hold | 20
674 | 2025-05-27 | CLOSED | 131
675 | 2025-05-27 | OPEN | 49
676 | 2025-05-28 | On Hold | 20
677 | 2025-05-28 | OPEN | 49
678 | 2025-05-28 | CLOSED | 131
679 | 2025-05-29 | OPEN | 49
680 | 2025-05-29 | CLOSED | 131
681 | 2025-05-29 | On Hold | 20
682 | 2025-05-30 | On Hold | 20
683 | 2025-05-30 | CLOSED | 131
684 | 2025-05-30 | OPEN | 49
685 | 2025-05-31 | On Hold | 20
686 | 2025-05-31 | CLOSED | 131
687 | 2025-05-31 | OPEN | 49
688 | 2025-06-01 | On Hold | 20
689 | 2025-06-01 | CLOSED | 131
690 | 2025-06-01 | OPEN | 49
691 | 2025-06-02 | OPEN | 49
692 | 2025-06-02 | CLOSED | 131
693 | 2025-06-02 | On Hold | 20
694 | 2025-06-03 | OPEN | 49
695 | 2025-06-03 | On Hold | 20
696 | 2025-06-03 | CLOSED | 131
697 | 2025-06-04 | On Hold | 20
698 | 2025-06-04 | OPEN | 49
699 | 2025-06-04 | CLOSED | 131
700 | 2025-06-05 | OPEN | 49
701 | 2025-06-05 | On Hold | 20
702 | 2025-06-05 | CLOSED | 131
703 | 2025-06-06 | On Hold | 20
704 | 2025-06-06 | OPEN | 49
705 | 2025-06-06 | CLOSED | 131
706 | 2025-06-07 | CLOSED | 131
707 | 2025-06-07 | On Hold | 20
708 | 2025-06-07 | OPEN | 49
709 | 2025-06-08 | On Hold | 20
710 | 2025-06-08 | OPEN | 49
711 | 2025-06-08 | CLOSED | 131
712 | 2025-06-09 | CLOSED | 131
713 | 2025-06-09 | On Hold | 20
714 | 2025-06-09 | OPEN | 49
715 | 2025-06-10 | CLOSED | 131
716 | 2025-06-10 | OPEN | 49
717 | 2025-06-10 | On Hold | 20
718 | 2025-06-11 | CLOSED | 131
719 | 2025-06-11 | OPEN | 49
720 | 2025-06-11 | On Hold | 20
721 | 2025-06-12 | OPEN | 49
722 | 2025-06-12 | CLOSED | 131
723 | 2025-06-12 | On Hold | 20
724 | 2025-06-13 | CLOSED | 131
725 | 2025-06-13 | OPEN | 49
726 | 2025-06-13 | On Hold | 20
727 | 2025-06-14 | On Hold | 20
728 | 2025-06-14 | OPEN | 49
729 | 2025-06-14 | CLOSED | 131
730 | 2025-06-15 | On Hold | 20
731 | 2025-06-15 | OPEN | 49
732 | 2025-06-15 | CLOSED | 131
733 | 2025-06-16 | CLOSED | 131
734 | 2025-06-16 | On Hold | 20
735 | 2025-06-16 | OPEN | 49
736 | 2025-06-17 | OPEN | 49
737 | 2025-06-17 | On Hold | 20
738 | 2025-06-17 | CLOSED | 131
739 | 2025-06-18 | OPEN | 49
740 | 2025-06-18 | On Hold | 20
741 | 2025-06-18 | CLOSED | 131
742 | 2025-06-19 | CLOSED | 131
743 | 2025-06-19 | OPEN | 49
744 | 2025-06-19 | On Hold | 20
745 | 2025-06-20 | On Hold | 20
746 | 2025-06-20 | OPEN | 49
747 | 2025-06-20 | CLOSED | 131
748 | 2025-06-21 | OPEN | 49
749 | 2025-06-21 | On Hold | 20
750 | 2025-06-21 | CLOSED | 131
751 | 2025-06-22 | On Hold | 20
752 | 2025-06-22 | CLOSED | 131
753 | 2025-06-22 | OPEN | 49
754 | 2025-06-23 | On Hold | 20
755 | 2025-06-23 | CLOSED | 131
756 | 2025-06-23 | OPEN | 49
757 | 2025-06-24 | On Hold | 20
758 | 2025-06-24 | CLOSED | 131
759 | 2025-06-24 | OPEN | 49
760 | 2025-06-25 | CLOSED | 131
761 | 2025-06-25 | On Hold | 20
762 | 2025-06-25 | OPEN | 49
763 | 2025-06-26 | OPEN | 44
764 | 2025-06-26 | On Hold | 20
765 | 2025-06-26 | CLOSED | 137
766 | 2025-06-27 | On Hold | 20
767 | 2025-06-27 | OPEN | 44
768 | 2025-06-27 | CLOSED | 137
769 | 2025-06-28 | On Hold | 20
770 | 2025-06-28 | OPEN | 44
771 | 2025-06-28 | CLOSED | 137
772 | 2025-06-29 | OPEN | 44
773 | 2025-06-29 | On Hold | 20
774 | 2025-06-29 | CLOSED | 137
775 | 2025-06-30 | On Hold | 20
776 | 2025-06-30 | CLOSED | 137
777 | 2025-06-30 | OPEN | 44
778 | 2025-07-01 | On Hold | 20
779 | 2025-07-01 | OPEN | 44
780 | 2025-07-01 | CLOSED | 137
781 | 2025-07-02 | On Hold | 20
782 | 2025-07-02 | CLOSED | 137
783 | 2025-07-02 | OPEN | 44
784 | 2025-07-03 | OPEN | 44
785 | 2025-07-03 | On Hold | 20
786 | 2025-07-03 | CLOSED | 137
787 | 2025-07-04 | On Hold | 20
788 | 2025-07-04 | CLOSED | 137
789 | 2025-07-04 | OPEN | 44
790 | 2025-07-05 | On Hold | 20
791 | 2025-07-05 | OPEN | 44
792 | 2025-07-05 | CLOSED | 137
793 | 2025-07-06 | CLOSED | 137
794 | 2025-07-06 | OPEN | 44
795 | 2025-07-06 | On Hold | 20
796 | 2025-07-07 | OPEN | 44
797 | 2025-07-07 | On Hold | 20
798 | 2025-07-07 | CLOSED | 137
799 | 2025-07-08 | On Hold | 20
800 | 2025-07-08 | CLOSED | 137
801 | 2025-07-08 | OPEN | 44
802 | 2025-07-09 | OPEN | 44
803 | 2025-07-09 | On Hold | 20
804 | 2025-07-09 | CLOSED | 137
805 | 2025-07-10 | OPEN | 44
806 | 2025-07-10 | On Hold | 20
807 | 2025-07-10 | CLOSED | 137
808 | 2025-07-11 | OPEN | 44
809 | 2025-07-11 | On Hold | 20
810 | 2025-07-11 | CLOSED | 137
811 | 2025-07-12 | On Hold | 20
812 | 2025-07-12 | OPEN | 44
813 | 2025-07-12 | CLOSED | 137
814 | 2025-07-13 | CLOSED | 137
815 | 2025-07-13 | OPEN | 44
816 | 2025-07-13 | On Hold | 20
817 | 2025-07-14 | On Hold | 20
818 | 2025-07-14 | OPEN | 44
819 | 2025-07-14 | CLOSED | 137
820 | 2025-07-15 | On Hold | 20
821 | 2025-07-15 | OPEN | 44
822 | 2025-07-15 | CLOSED | 137
823 | 2025-07-16 | On Hold | 20
824 | 2025-07-16 | OPEN | 44
825 | 2025-07-16 | CLOSED | 137
826 | 2025-07-17 | On Hold | 20
827 | 2025-07-17 | CLOSED | 137
828 | 2025-07-17 | OPEN | 44
829 | 2025-07-18 | On Hold | 20
830 | 2025-07-18 | OPEN | 44
831 | 2025-07-18 | CLOSED | 137
832 | 2025-07-19 | OPEN | 44
833 | 2025-07-19 | On Hold | 20
834 | 2025-07-19 | CLOSED | 137
835 | 2025-07-20 | On Hold | 20
836 | 2025-07-20 | CLOSED | 137
837 | 2025-07-20 | OPEN | 44
838 | 2025-07-21 | On Hold | 20
839 | 2025-07-21 | CLOSED | 137
840 | 2025-07-21 | OPEN | 44
841 | 2025-07-22 | OPEN | 44
842 | 2025-07-22 | CLOSED | 137
843 | 2025-07-22 | On Hold | 20
844 | 2025-07-23 | On Hold | 20
845 | 2025-07-23 | OPEN | 44
846 | 2025-07-23 | CLOSED | 137
847 | 2025-07-24 | On Hold | 20
848 | 2025-07-24 | CLOSED | 137
849 | 2025-07-24 | OPEN | 44
850 | 2025-07-25 | OPEN | 44
851 | 2025-07-25 | On Hold | 20
852 | 2025-07-25 | CLOSED | 137
853 | 2025-07-26 | On Hold | 20
854 | 2025-07-26 | CLOSED | 137
855 | 2025-07-26 | OPEN | 44
856 | 2025-07-27 | On Hold | 20
857 | 2025-07-27 | CLOSED | 137
858 | 2025-07-27 | OPEN | 44
859 | 2025-07-28 | OPEN | 44
860 | 2025-07-28 | CLOSED | 137
861 | 2025-07-28 | On Hold | 20
862 | 2025-07-29 | CLOSED | 137
863 | 2025-07-29 | OPEN | 44
864 | 2025-07-29 | On Hold | 20
865 | 2025-07-30 | CLOSED | 137
866 | 2025-07-30 | On Hold | 20
867 | 2025-07-30 | OPEN | 44
868 | 2025-07-31 | OPEN | 44
869 | 2025-07-31 | On Hold | 20
870 | 2025-07-31 | CLOSED | 137
871 | 2025-08-01 | CLOSED | 137
872 | 2025-08-01 | On Hold | 20
873 | 2025-08-01 | OPEN | 44
874 | 2025-08-02 | OPEN | 44
875 | 2025-08-02 | CLOSED | 137
876 | 2025-08-02 | On Hold | 20
877 | 2025-08-03 | OPEN | 44
878 | 2025-08-03 | CLOSED | 137
879 | 2025-08-03 | On Hold | 20
880 | 2025-08-04 | CLOSED | 137
881 | 2025-08-04 | On Hold | 20
882 | 2025-08-04 | OPEN | 44
883 | 2025-08-05 | OPEN | 44
884 | 2025-08-05 | CLOSED | 137
885 | 2025-08-05 | On Hold | 20
886 | 2025-08-06 | On Hold | 20
887 | 2025-08-06 | CLOSED | 137
888 | 2025-08-06 | OPEN | 44
889 | 2025-08-07 | On Hold | 20
890 | 2025-08-07 | OPEN | 44
891 | 2025-08-07 | CLOSED | 137
892 | 2025-08-08 | OPEN | 44
893 | 2025-08-08 | CLOSED | 137
894 | 2025-08-08 | On Hold | 20
895 | 2025-08-09 | CLOSED | 137
896 | 2025-08-09 | On Hold | 20
897 | 2025-08-09 | OPEN | 44
898 | 2025-08-10 | OPEN | 44
899 | 2025-08-10 | CLOSED | 137
900 | 2025-08-10 | On Hold | 20
901 | 2025-08-11 | CLOSED | 137
902 | 2025-08-11 | OPEN | 44
903 | 2025-08-11 | On Hold | 20
904 | 2025-08-12 | CLOSED | 137
905 | 2025-08-12 | On Hold | 20
906 | 2025-08-12 | OPEN | 44
907 | 2025-08-13 | CLOSED | 137
908 | 2025-08-13 | On Hold | 20
909 | 2025-08-13 | OPEN | 44
910 | 2025-08-14 | OPEN | 44
911 | 2025-08-14 | CLOSED | 137
912 | 2025-08-14 | On Hold | 20
913 | 2025-08-15 | On Hold | 20
914 | 2025-08-15 | OPEN | 44
915 | 2025-08-15 | CLOSED | 137
916 | 2025-08-16 | CLOSED | 137
917 | 2025-08-16 | OPEN | 44
918 | 2025-08-16 | On Hold | 20
919 | 2025-08-17 | OPEN | 44
920 | 2025-08-17 | CLOSED | 137
921 | 2025-08-17 | On Hold | 20
922 | 2025-08-18 | On Hold | 20
923 | 2025-08-18 | OPEN | 44
924 | 2025-08-18 | CLOSED | 137
925 | 2025-08-19 | OPEN | 44
926 | 2025-08-19 | CLOSED | 137
927 | 2025-08-19 | On Hold | 20
928 | 2025-08-20 | CLOSED | 137
929 | 2025-08-20 | OPEN | 44
930 | 2025-08-20 | On Hold | 20
931 | 2025-08-21 | OPEN | 44
932 | 2025-08-21 | On Hold | 20
933 | 2025-08-21 | CLOSED | 137
934 | 2025-08-22 | CLOSED | 137
935 | 2025-08-22 | On Hold | 20
936 | 2025-08-22 | OPEN | 44
937 | 2025-08-23 | CLOSED | 137
938 | 2025-08-23 | On Hold | 20
939 | 2025-08-23 | OPEN | 44
940 | 2025-08-24 | CLOSED | 137
941 | 2025-08-24 | OPEN | 44
942 | 2025-08-24 | On Hold | 20
943 | 2025-08-25 | On Hold | 20
944 | 2025-08-25 | CLOSED | 137
945 | 2025-08-25 | OPEN | 44
946 | 2025-08-26 | OPEN | 44
947 | 2025-08-26 | CLOSED | 137
948 | 2025-08-26 | On Hold | 20
949 | 2025-08-27 | On Hold | 20
950 | 2025-08-27 | OPEN | 44
951 | 2025-08-27 | CLOSED | 137
952 | 2025-08-28 | OPEN | 44
953 | 2025-08-28 | CLOSED | 137
954 | 2025-08-28 | On Hold | 20
955 | 2025-08-29 | CLOSED | 137
956 | 2025-08-29 | OPEN | 44
957 | 2025-08-29 | On Hold | 20
958 | 2025-08-30 | On Hold | 20
959 | 2025-08-30 | CLOSED | 137
960 | 2025-08-30 | OPEN | 44
961 | 2025-08-31 | On Hold | 20
962 | 2025-08-31 | OPEN | 44
963 | 2025-08-31 | CLOSED | 137
964 | 2025-09-01 | On Hold | 20
965 | 2025-09-01 | CLOSED | 137
966 | 2025-09-01 | OPEN | 44
967 | 2025-09-02 | On Hold | 20
968 | 2025-09-02 | CLOSED | 137
969 | 2025-09-02 | OPEN | 44
970 | 2025-09-03 | OPEN | 44
971 | 2025-09-03 | On Hold | 20
972 | 2025-09-03 | CLOSED | 137
973 | 2025-09-04 | On Hold | 20
974 | 2025-09-04 | CLOSED | 137
975 | 2025-09-04 | OPEN | 44
976 | 2025-09-05 | On Hold | 20
977 | 2025-09-05 | CLOSED | 137
978 | 2025-09-05 | OPEN | 44
979 | 2025-09-06 | On Hold | 20
980 | 2025-09-06 | OPEN | 44
981 | 2025-09-06 | CLOSED | 137
982 | 2025-09-07 | On Hold | 20
983 | 2025-09-07 | OPEN | 44
984 | 2025-09-07 | CLOSED | 137
985 | 2025-09-08 | OPEN | 44
986 | 2025-09-08 | CLOSED | 137
987 | 2025-09-08 | On Hold | 20
988 | 2025-09-09 | On Hold | 20
989 | 2025-09-09 | OPEN | 44
990 | 2025-09-09 | CLOSED | 137
991 | 2025-09-10 | On Hold | 20
992 | 2025-09-10 | CLOSED | 137
993 | 2025-09-10 | OPEN | 44
994 | 2025-09-11 | OPEN | 44
995 | 2025-09-11 | On Hold | 20
996 | 2025-09-11 | CLOSED | 137
997 | 2025-09-12 | OPEN | 44
998 | 2025-09-12 | On Hold | 20
999 | 2025-09-12 | CLOSED | 137
1000 | 2025-09-13 | OPEN | 44
1001 | 2025-09-13 | CLOSED | 137
1002 | 2025-09-13 | On Hold | 20
1003 | 2025-09-14 | OPEN | 44
1004 | 2025-09-14 | On Hold | 20
1005 | 2025-09-14 | CLOSED | 137
1006 | 2025-09-15 | OPEN | 44
1007 | 2025-09-15 | CLOSED | 137
1008 | 2025-09-15 | On Hold | 20
1009 | 2025-09-16 | OPEN | 44
1010 | 2025-09-16 | CLOSED | 137
1011 | 2025-09-16 | On Hold | 20
1012 | 2025-09-17 | On Hold | 20
1013 | 2025-09-17 | CLOSED | 137
1014 | 2025-09-17 | OPEN | 44
1015 | 2025-09-18 | On Hold | 20
1016 | 2025-09-18 | OPEN | 44
1017 | 2025-09-18 | CLOSED | 137
1018 | 2025-09-19 | On Hold | 20
1019 | 2025-09-19 | CLOSED | 137
1020 | 2025-09-19 | OPEN | 44
1021 | 2025-09-20 | CLOSED | 137
1022 | 2025-09-20 | OPEN | 44
1023 | 2025-09-20 | On Hold | 20
1024 | 2025-09-21 | CLOSED | 137
1025 | 2025-09-21 | On Hold | 20
1026 | 2025-09-21 | OPEN | 44
1027 | 2025-09-22 | CLOSED | 137
1028 | 2025-09-22 | OPEN | 44
1029 | 2025-09-22 | On Hold | 20
1030 | 2025-09-23 | On Hold | 20
1031 | 2025-09-23 | OPEN | 44
1032 | 2025-09-23 | CLOSED | 137
1033 | 2025-09-24 | On Hold | 20
1034 | 2025-09-24 | CLOSED | 137
1035 | 2025-09-24 | OPEN | 44
1036 | 2025-09-25 | OPEN | 44
1037 | 2025-09-25 | On Hold | 20
1038 | 2025-09-25 | CLOSED | 137
1039 | 2025-09-26 | CLOSED | 137
1040 | 2025-09-26 | On Hold | 20
1041 | 2025-09-26 | OPEN | 44
1042 | 2025-09-27 | OPEN | 44
1043 | 2025-09-27 | On Hold | 20
1044 | 2025-09-27 | CLOSED | 137
1045 | 2025-09-28 | OPEN | 44
1046 | 2025-09-28 | On Hold | 20
1047 | 2025-09-28 | CLOSED | 137
1048 | 2025-09-29 | On Hold | 20
1049 | 2025-09-29 | CLOSED | 137
1050 | 2025-09-29 | OPEN | 44
1051 | 2025-09-30 | On Hold | 20
1052 | 2025-09-30 | CLOSED | 137
1053 | 2025-09-30 | OPEN | 44
1054 | 2025-10-01 | On Hold | 20
1055 | 2025-10-01 | OPEN | 44
1056 | 2025-10-01 | CLOSED | 137
1057 | 2025-10-02 | On Hold | 20
1058 | 2025-10-02 | CLOSED | 137
1059 | 2025-10-02 | OPEN | 44
1060 | 2025-10-03 | On Hold | 20
1061 | 2025-10-03 | CLOSED | 137
1062 | 2025-10-03 | OPEN | 44
1063 | 2025-10-04 | OPEN | 44
1064 | 2025-10-04 | On Hold | 20
1065 | 2025-10-04 | CLOSED | 137
1066 | 2025-10-05 | CLOSED | 137
1067 | 2025-10-05 | On Hold | 20
1068 | 2025-10-05 | OPEN | 44
1069 | 2025-10-06 | On Hold | 20
1070 | 2025-10-06 | OPEN | 44
1071 | 2025-10-06 | CLOSED | 137
1072 | 2025-10-07 | On Hold | 20
1073 | 2025-10-07 | OPEN | 44
1074 | 2025-10-07 | CLOSED | 137
1075 | 2025-10-08 | CLOSED | 137
1076 | 2025-10-08 | On Hold | 20
1077 | 2025-10-08 | OPEN | 44
1078 | 2025-10-09 | On Hold | 20
1079 | 2025-10-09 | CLOSED | 137
1080 | 2025-10-09 | OPEN | 44
1081 | 2025-10-10 | On Hold | 20
1082 | 2025-10-10 | OPEN | 44
1083 | 2025-10-10 | CLOSED | 137
1084 | 2025-10-11 | OPEN | 44
1085 | 2025-10-11 | On Hold | 20
1086 | 2025-10-11 | CLOSED | 137
1087 | 2025-10-12 | OPEN | 44
1088 | 2025-10-12 | CLOSED | 137
1089 | 2025-10-12 | On Hold | 20
1090 | 2025-10-13 | On Hold | 20
1091 | 2025-10-13 | CLOSED | 137
1092 | 2025-10-13 | OPEN | 44
1093 | 2025-10-14 | OPEN | 44
1094 | 2025-10-14 | On Hold | 20
1095 | 2025-10-14 | CLOSED | 137
1096 | 2025-10-15 | OPEN | 44
1097 | 2025-10-15 | On Hold | 20
1098 | 2025-10-15 | CLOSED | 137
1099 | 2025-10-16 | OPEN | 44
1100 | 2025-10-16 | CLOSED | 137
1101 | 2025-10-16 | On Hold | 20
1102 | 2025-10-17 | On Hold | 20
1103 | 2025-10-17 | CLOSED | 137
1104 | 2025-10-17 | OPEN | 44
1105 | 2025-10-18 | CLOSED | 137
1106 | 2025-10-18 | On Hold | 20
1107 | 2025-10-18 | OPEN | 44
1108 | 2025-10-19 | On Hold | 20
1109 | 2025-10-19 | OPEN | 44
1110 | 2025-10-19 | CLOSED | 137
1111 | 2025-10-20 | CLOSED | 137
1112 | 2025-10-20 | On Hold | 20
1113 | 2025-10-20 | OPEN | 44
1114 | 2025-10-21 | OPEN | 44
1115 | 2025-10-21 | On Hold | 20
1116 | 2025-10-21 | CLOSED | 137
1117 | 2025-10-22 | On Hold | 20
1118 | 2025-10-22 | CLOSED | 137
1119 | 2025-10-22 | OPEN | 44
1120 | 2025-10-23 | OPEN | 44
1121 | 2025-10-23 | CLOSED | 137
1122 | 2025-10-23 | On Hold | 20
1123 | 2025-10-24 | OPEN | 44
1124 | 2025-10-24 | CLOSED | 137
1125 | 2025-10-24 | On Hold | 20
1126 | 2025-10-25 | On Hold | 20
1127 | 2025-10-25 | OPEN | 44
1128 | 2025-10-25 | CLOSED | 137
1129 | 2025-10-26 | On Hold | 20
1130 | 2025-10-26 | OPEN | 44
1131 | 2025-10-26 | CLOSED | 137
1132 | 2025-10-27 | On Hold | 20
1133 | 2025-10-27 | CLOSED | 137
1134 | 2025-10-27 | OPEN | 44
1135 | 2025-10-28 | On Hold | 20
1136 | 2025-10-28 | OPEN | 44
1137 | 2025-10-28 | CLOSED | 137
1138 | 2025-10-29 | On Hold | 20
1139 | 2025-10-29 | CLOSED | 137
1140 | 2025-10-29 | OPEN | 44
1141 | 2025-10-30 | On Hold | 20
1142 | 2025-10-30 | OPEN | 44
1143 | 2025-10-30 | CLOSED | 137
1144 | 2025-10-31 | CLOSED | 137
1145 | 2025-10-31 | OPEN | 44
1146 | 2025-10-31 | On Hold | 20
1147 | 2025-11-01 | On Hold | 20
1148 | 2025-11-01 | CLOSED | 137
1149 | 2025-11-01 | OPEN | 44
1150 | 2025-11-02 | On Hold | 20
1151 | 2025-11-02 | CLOSED | 137
1152 | 2025-11-02 | OPEN | 44
1153 | 2025-11-03 | CLOSED | 137
1154 | 2025-11-03 | OPEN | 44
1155 | 2025-11-03 | On Hold | 20

## Versioncontrol
ProjectID | Project Name | Software | Customer | Versions | VersionInformation
PRO2 | EOL For Capacitive Touch Snake Sensor | MTS | NAXNOVA | v1.0.0
PRO3 | ICT for Pluggable Residual and Current Detector | MTS | Avalon | v1.0.1
PRO4 | On Board Charger Hella | MTS | HELLA | v1.0.1
PRO5 | EOL Tester for Instrument cluster-Indication instrument | MTS | Indication Instruments | V2.0.0
PRO6 | Avalon OBC And DTU | MTS | Avalon | v1.0.1
PRO7 | Assembly line for ECU -west port -syrma | Traceware | Syrma -westport | V2.0.1
PRO8 | Yazaki Traceability | Traceware | Yazaki | V1.0.1
PRO9 | Assembly line for OBC 3.3KW | Traceware | Minda | V2.0.0
PRO10 | Grading Machine for MOSFET | MTS | Turntide | V3.0.0
PRO13 | EOL For Wireless Chargeing Module(WCM) | MTS | Minda | v1.0.1
PRO14 | EOL for 48V MCU | MTS | Mahindra | V5.0.0
PRO16 | Yazaki Traceability(Line2,Line3&Line4) | Traceware | Yazaki | V1.0.1
PRO17 | FTM for WCM | MTS | Minda | V1.0.1
PRO18 | MCU Existing Line Traceability | Traceware | Turntide | V1.0.1& V2.0.1
PRO19 | USB Charger | MTS | Yazaki | V1.0.1
PRO20 | EOL For Capacitive Touch Snake Sensor(Additional variant) | MTS | NAXNOVA | v1.0.0
PRO21 | River Rider | MTS | Suprajith | v1.0.0
PRO22 | Indicator testing | MTS | Honda | v4.0.0
PRO23 | BCON1_CONTROLLER | MTS | Lumax | v1.0.1
PRO24 | BCON2_SWITCH | MTS | Lumax | v1.0.1
PRO25 | BCON3_Key | MTS | Lumax | v1.0.2 ,v6.0.0&v7.0.0
PRO26 | Functional Tester for VCU PCBA | MTS | Syrma | v1.0.2